# League Execution

# MCD Mini League (MML)

## League Execution Document

## 1. How the League Will Be Planned

### 1.1 Pre-Planning Phase (Post Tender – Weeks 1 to 4)

The planning phase begins immediately after the tender is awarded and the agreement is signed.

| Week | Planning Activity | Responsible |
| --- | --- | --- |
| Week 1 | Form central operations team; sign MOU with MCD | League Director |
| Week 1-2 | Issue official notices (MCD, DoE Delhi, AIFF, DCA) to all schools | MCD + Khelo Tech |
| Week 2 | Finalize 12 MCD clubs (one per zone) | MCD Zone Coordinators |
| Week 2-3 | Onboard 68 non-MCD clubs (single-school + clusters) | Khelo Tech Onboarding Team |
| Week 3 | Register players (5,100+ children) on GMS | Club Managers |
| Week 3-4 | Verify age proofs (U-9 & U-11) | Zone Coordinators |
| Week 4 | Form 4 teams per club (U-9 Boys, U-9 Girls, U-11 Boys, U-11 Girls) | Club Managers |
| Week 4 | Allocate venues across 12 zones; prepare mini-fields | Zone Operations Leads |

### 1.2 Season Structure (5 Weeks Total)

| Phase | Duration | Format | Matches |
| --- | --- | --- | --- |
| Phase 1 – Qualification | 3 matchdays | Sub-league (10 pools → 2 sub-pools of 4 teams → round-robin) | 480 per sport |
| Phase 2 – Main League | 5 matchdays | 32-team knockout with byes | 384 per sport |
| Total | 5 weeks |  | 864 per sport |

### 1.3 Key Planning Decisions

| Decision Point | Outcome |
| --- | --- |
| Age categories | U-9 & U-11 (Boys & Girls) |
| Sports | Football & Cricket |
| Club model | 80 clubs (12 MCD + 68 non-MCD) |
| Pyramid tiers | Bronze (20), Silver (20), Gold (20), Diamond (20) |
| Promotion/Relegation | The top 4 move up, and the Bottom 4 move down |
| Talent focus | Every match generates data for scouting |

## 2. How the League Will Operate

### 2.1 Club-Based Operational Model

| Club Type | Number | Fee | Formation |
| --- | --- | --- | --- |
| MCD Clubs | 12 | Free (CSR) | One per zone, grouping MCD schools |
| Non-MCD Clubs | 68 | ₹25,000/sport | Single school OR cluster of 2-3 schools |

Each club fields 4 teams per sport: U-9 Boys, U-9 Girls, U-11 Boys, U-11 Girls

### 2.2 Phase 1 – Qualification Stage Operation

| Step | Description |
| --- | --- |
| 1 | 80 teams per category divided into 10 Pools of 8 teams |
| 2 | Each Pool split into 2 Sub-Pools (A & B) of 4 teams |
| 3 | Single round-robin within each Sub-Pool (3 matches per team) |
| 4 | The top 1 team from each Sub-Pool qualifies → 20 teams advance |

### 2.3 Phase 2 – Knockout Stage Operation

| Step | Description |
| --- | --- |
| 1 | 20 qualified teams + 12 BYES → 32-team knockout bracket |
| 2 | Teams randomly seeded by GMS algorithm |
| 3 | Knockout matches: Round of 32 → Round of 16 → QF → SF → Final |
| 4 | Champion crowned for each category |

### 2.4 Zone-Wise Operations (12 Zones)

| Role | Responsibility |
| --- | --- |
| MCD Zone Coordinator | Approvals, infrastructure, escalations |
| Khelo Tech Zone Operations Lead | Fixtures, venues, match coordination |
| Venue Coordinator | Ground readiness, mini-field preparation, logistics |
| MCD Teachers & PETs (as Referees/Umpires) | Match officiating |

### 2.5 Promotion & Relegation (End of Each Season)

| League | Promoted | Relegated |
| --- | --- | --- |
| Diamond | Champion crowned | Bottom 4 to Gold |
| Gold | Top 4 to Diamond | Bottom 4 to Silver |
| Silver | Top 4 to Gold | Bottom 4 to Bronze |
| Bronze | Top 4 to Silver | Champion crowned |

## 3. How Matches Will Be Conducted

### 3.1 Match Format Summary

| Parameter | Football | Cricket |
| --- | --- | --- |
| Format | 7v7 | 11v11 |
| Team size (min-max) | 12-16 players | 15-16 players |
| Match duration | 15 min per half (30 min total) + 5-10 min break | 8-10 overs per innings (tennis ball) |
| Ball type | Standard football (size 3 for U-9, size 4 for U-11) | Tennis ball |

### 3.2 Stadium Configuration

#### Football Stadiums

| Parameter | Details |
| --- | --- |
| Number of stadiums | 2 |
| Mini fields per stadium | 4 mini fields |
| Total mini fields | 8 mini fields |
| Matches per mini field per day | 4-6 matches (depending on schedule) |
| Total matches possible per day (both stadiums) | 32-48 matches |

#### Cricket Stadiums

| Parameter | Details |
| --- | --- |
| Number of stadiums | 2 |
| Mini fields per stadium | 2-3 mini fields |
| Total mini fields | 4-6 mini fields |
| Matches per mini field per day | 3-4 matches |
| Total matches possible per day (both stadiums) | 12-24 matches |

### 3.3 Match-Day Timeline Football (30 min match + break)

| Time | Activity | Responsible |
| --- | --- | --- |
| T-45 min | Venue readiness check (4 mini fields) | Venue Coordinator |
| T-30 min | Team arrival, attendance marking on GMS | Club Manager |
| T-15 min | Referee arrival (MCD teacher/PET), equipment check, coin toss | Referee |
| T-0 | Match kick-off (15 min first half) | Referee |
| T+15 | Half-time break (5-10 min) | Referee |
| T+20 to T+25 | Second half kick-off | Referee |
| T+35 to T+40 | Final whistle, result entry on GMS | Referee |
| T+45 | Match closure, leaderboard update | System |

### 3.4 Match-Day Timeline Cricket (8-10 overs per innings)

| Time | Activity | Responsible |
| --- | --- | --- |
| T-60 min | Venue readiness (pitch preparation, boundary marking) | Venue Coordinator |
| T-30 min | Team arrival, attendance verification, coin toss | Club Manager |
| T-0 | Match start – First innings (8-10 overs) | Umpires (MCD teachers) |
| T+30 to T+40 | Innings break (10 min) | Umpires |
| T+40 to T+50 | Second innings starts | Umpires |
| T+70 to T+90 | Match end, result entry on GMS | Umpires |
| T+90 | Match closure, photos upload | Umpires + Coaches |

### 3.5 Age-Specific Match Parameters

| Aspect | U-9 Football | U-11 Football | U-9 Cricket | U-11 Cricket |
| --- | --- | --- | --- | --- |
| Format | 7v7 | 7v7 | 11v11 | 11v11 |
| Team size | 12-16 players | 12-16 players | 15-16 players | 15-16 players |
| Match duration | 15 min halves | 15 min halves | 8 overs/innings | 10 overs/innings |
| Half-time break | 5-10 min | 5-10 min | 10 min | 10 min |
| Ball | Size 3 | Size 4 | Tennis ball | Tennis ball |
| Playing field | Mini field (approx 40x30m) | Mini field (approx 50x35m) | 20-25m boundary | 25-30m boundary |

### 3.6 Attendance & Age Verification

| Step | Method |
| --- | --- |
| Pre-match | Coach marks present players on GMS |
| Verification | Referee cross-checks with uploaded ID proofs |
| Spot check | 10% of players randomly checked for age proof |

### 3.7 Medical Support

| Level | Availability |
| --- | --- |
| Basic first aid | Mandatory at every mini field |
| Stretcher | Minimum 2 per stadium |
| Ambulance on call | 1 per stadium |
| Medical room | Available at each stadium |

### 3.8 Match Closure Process

| Step | Action |
| --- | --- |
| 1 | Referee/Umpire submits final score on GMS |
| 2 | Both club managers verify digitally |
| 3 | System locks match – no further edits |
| 4 | Standings (Phase 1) or bracket (Phase 2) updated |
| 5 | Player statistics updated (goals, wickets, catches, etc.) |
| 6 | Match report generated |

### 3.9 Total Matches Execution Capacity

| Sport | Stadiums | Mini Fields | Matches per Day (approx) | Days to Complete 864 Matches |
| --- | --- | --- | --- | --- |
| Football | 2 | 8 | 32-48 | 18-27 days |
| Cricket | 2 | 4-6 | 12-24 | 36-72 days |

Note: Matches will be scheduled concurrently across all mini fields to complete the league within the 5-week window.

## 4. How Technology Will Support Execution

### 4.1 Game Management System (GMS) – Core Modules

| Module | Function |
| --- | --- |
| Club Registration | Onboard MCD & non-MCD clubs, fee collection |
| Player Registration | Age-proof onboarding, bulk upload |
| Age Verification | Automated validation against birth certificates/Aadhaar |
| Pool & Fixture Management | 10 pools → 2 sub-pools → auto-scheduling |
| Knockout Draw Engine | 32-team bracket with random seeding + byes |
| Results System | Live score entry, validation, photo upload |
| Zone Dashboards | 12 individual views for zone coordinators |
| Athlete Profiles | Lifecycle performance tracking (U-9 → U-11 → senior) |
| Talent Identification Engine | Scientific scouting markers |
| Digital Certificates | Auto-generated participation & achievement certs |
| Notification Engine | SMS/Email/In-app alerts |
| Venue Management | Mini field allocation, real-time utilization tracking |

### 4.2 How Real-Time Updates Happen

The referee submits result on GMS app.

↓

Central GMS Server (<2 sec latency)

↓

Auto-update standings/bracket (instant)

↓

Refresh Zone Dashboard (instant)

↓

Push notification to club managers + parents (<10 sec)

### 4.3 How MCD Monitors Operations

| Dashboard | Access | Refresh |
| --- | --- | --- |
| Central Sports Cell Dashboard | MCD Commissioner | Real-time |
| Zone Coordinator Dashboard | 12 zone admins | Real-time |
| Venue Utilization Dashboard (mini fields) | Operations team | Real-time |
| Talent ID Dashboard | Scouting team | Daily |

### 4.4 How Data Is Collected Centrally

| Source | Data Collected |
| --- | --- |
| Club registration | Club name, zone, contact, fee status |
| Player registration | Name, age (U-9/U-11), school, zone, guardian |
| Match results (Phase 1) | Scores, goals/wickets, cards |
| Match results (Phase 2) | Knockout progression, finals |
| Referee app | Match photos, incident reports |
| Coach app | Attendance, player ratings |

Data storage: Encrypted cloud servers with daily backup. MCD retains full ownership of all data.

### 4.5 Digital Certificates – Automated

| Trigger | Certificate |
| --- | --- |
| Player completes 1 match | Participation certificate |
| Player completes 5+ matches | Achievement certificate |
| Player qualifies for Phase 2 | Qualification certificate |
| Team wins league/championship | Winner certificate |
| Player gets talent tag | Talent recognition certificate |
| End of season | Season completion certificate |

## 5. How Governance and Reporting Will Work

### 5.1 Governance Hierarchy

MCD Commissioner

│

↓

League Director (Khelo Tech + MCD liaison)

│

├── Technology Lead

├── Operations Head

├── Sponsorship Lead

└── Talent Scouting Head

│

↓ (per zone)

Zone Coordinator (MCD) ←→ Zone Operations Lead (Khelo Tech)

│

├── Venue Coordinators (1 per stadium)

├── Mini Field Supervisors (1 per mini field)

└── MCD Teachers & PETs (Referees/Umpires)

### 5.2 Central Operations Team (City Level)

| Role | Number | Responsibility |
| --- | --- | --- |
| League Director | 1 | Overall strategy, MCD liaison |
| Technology Lead | 1 | GMS uptime, data security |
| Operations Head | 1 | All zones execution both sports |
| Sponsorship & Marketing Lead | 1 | CSR & partner management |
| Talent Scouting Head | 1 | Talent ID framework |

### 5.3 Zone-Level Structure (Per Zone)

| Role | Number per Zone | Responsibility |
| --- | --- | --- |
| Zone Coordinator (MCD) | 1 | Approvals, infrastructure, escalations |
| Zone Operations Lead | 1 | Fixture adherence, venue coordination |
| Venue Coordinators | 2 (one per stadium) | Stadium readiness |
| Mini Field Supervisors | 4-6 per zone | Mini field readiness, match flow |
| MCD Teachers & PETs (Referees/Umpires) | 10-15 per zone | Match officiating |

### 5.4 Escalation Matrix

| Issue Level | Definition | First Contact | Resolution Time | Final Authority |
| --- | --- | --- | --- | --- |
| Level 1 | Minor (score dispute, late team) | Referee + Mini Field Supervisor | 15 mins | Zone Ops Lead |
| Level 2 | Moderate (venue issue, weather) | Zone Ops Lead | 2 hours | Zone Coordinator |
| Level 3 | Major (injury, crowd dispute) | Zone Coordinator | 4 hours | League Director |
| Level 4 | Critical (legal, media, government) | League Director + MCD | 24 hours | MCD Commissioner |

### 5.5 Reporting Structure

#### Daily Reports

| Report | Content | Recipient |
| --- | --- | --- |
| Match Summary | Scores, venues, attendance for day (both sports) | Zone Coordinators |
| Mini Field Utilization | Usage % of each mini field | Operations Head |
| Incident Log | Injuries, disputes, red cards | League Director |

#### Weekly Reports

| Report | Content | Recipient |
| --- | --- | --- |
| Zone Performance Dashboard | Participation %, matches completed, talent tags per zone | MCD Central |
| Talent Identification Report | High-potential athletes flagged | Talent Scouting Head |
| Phase 1 Standings | Sub-pool leaders, qualification status | All clubs |

#### End-Season Reports

| Report | Content | Recipient |
| --- | --- | --- |
| League Summary | Complete standings, promotion/relegation | All stakeholders |
| Talent Pipeline Report | U-9 → U-11 progression, academy recommendations | MCD Sports Cell |
| Zone-Wise Analytics | Comparison across 12 zones | MCD Commissioner |
| Sponsor Impact Report | Brand visibility, reach | Sponsors |

## 6. How the Overall Ecosystem Will Function at Scale Across Delhi

### 6.1 Scale Parameters

| Parameter | Value |
| --- | --- |
| MCD schools | 1,512 |
| Zones | 12 |
| Student base | 6.5 lakh+ |
| Sports | Football, Cricket |
| Age groups | U-9, U-11 |
| Gender | Boys & Girls |
| Total clubs | 80 |
| Total teams | 320 (80 clubs × 4 teams) |
| Total children | 5,100+ |
| Total matches per sport | 864 |
| Season duration | 5 weeks |

### 6.2 Infrastructure at Scale

| Sport | Stadiums | Mini Fields | Matches per Day Capacity |
| --- | --- | --- | --- |
| Football | 2 | 8 | 32-48 |
| Cricket | 2 | 4-6 | 12-24 |

### 6.3 Long-Term Athlete Pathway

U-9 Season 1 (Bronze/Silver)

↓ (promotion + development)

U-9 Season 2 (Silver/Gold)

↓ (age progression + talent tag)

U-11 Season 1 (Gold/Diamond)

↓ (elite performance)

MCD-Affiliated Academy (MOU with Top 10 Diamond Clubs)

↓

Delhi State Teams / Khelo India / National Pathways

### 6.5 Sustainability at Scale

| Element | How It Scales |
| --- | --- |
| 10-year IP rights (Khelo Tech) | Long-term platform stability |
| Sponsorship model | Non-MCD club fees + CSR funding |
| MCD infrastructure | 1,512 schools + stadiums – no capital expenditure |
| MCD teachers & PETs | Provided by MCD for match officiating – no external hiring |
| Digital-first operations | GMS scales to 1,000+ matches without adding administrators |
| Mini field model | 8 football + 4-6 cricket mini fields enable parallel matches |

## 7. Total Manpower (MCD-Provided Teachers & Coaches)

### 7.1 Manpower Philosophy

MCD will provide their existing teachers and PETs (Physical Education Teachers) to serve as referees, umpires, and match officials. This approach ensures:

- No additional hiring cost – Utilizing existing MCD workforce

- Familiarity with children – Teachers already know the students

- Trust & accountability – MCD employees are accountable to MCD

- Skill development – Teachers get trained in sports officiating

### 7.2 MCD-Provided Manpower Requirement

| Role | Number Required | Provided By |
| --- | --- | --- |
| Referees (Football) | 8 per match-day | MCD (PETs/Teachers) |
| Umpires (Cricket) | 8-12 per match-day | MCD (PETs/Teachers) |
| Scorers (Cricket) | 4-6 per match-day | MCD (Teachers) |
| Zone Coordinators | 12 | MCD (Education Dept) |
| Total MCD-Provided | ~32-38 per match-day |  |

### 7.3 Match-Day Manpower Breakdown

#### Football (2 Stadiums, 8 Mini Fields)

| Role | Per Mini Field | Per Stadium | Total (2 Stadiums) | Provided By |
| --- | --- | --- | --- | --- |
| Referee | 1 | 4 | 8 | MCD (PETs/Teachers) |
| Total Football Match-Day |  |  | 8 |  |

#### Cricket (2 Stadiums, 4-6 Mini Fields)

| Role | Per Mini Field | Per Stadium | Total (2 Stadiums) | Provided By |
| --- | --- | --- | --- | --- |
| Umpire | 2 | 4-6 | 8-12 | MCD (PETs/Teachers) |
| Scorer | 1 | 2-3 | 4-6 | MCD (Teachers) |
| Total Cricket Match-Day |  |  | 12-18 |  |

### 7.4 Total Manpower Summary

| Level | Number of Personnel | Provided By | Type |
| --- | --- | --- | --- |
| Central Operations (Tech, Ops, Sponsorship, Talent) | 5 | Khelo Tech | Full-time |
| Zone Operations Leads | 12 | Khelo Tech | Full-time |
| Venue Coordinators | 4 (2 per sport) | Khelo Tech | Full-time (match-day) |
| Mini Field Supervisors | 12-14 | Khelo Tech | Part-time (match-day) |
| MCD Teachers & PETs (Referees/Umpires/Scorers) | 20-26 per match-day | MCD | Match-day |
| MCD Zone Coordinators | 12 | MCD | Part-time (oversight) |
| Total Operational Manpower | ~65-73 | Mixed |  |

# Clubs Onboarding Procedure

# MCD Mini League (MML)

## Club Onboarding & Supervision Framework Document

## 1. Core Motive of the League

The primary motive of the MCD Mini League is to identify and nurture grassroots-level talent across Delhi-NCR.

The league is not just about competition or participation; it is a structured, technology-driven talent scouting ecosystem designed to discover young athletes (U-9 & U-11) in football and cricket, create digital athlete profiles, and build a sustainable pipeline of sporting talent for Delhi and the nation.

Every match, every registration, and every data point collected serves this single purpose: finding the next generation of champions at the grassroots level.

## 2. Onboarding Strategy Overview

### 2.1 The Onboarding Challenge

| Metric | Number |
| --- | --- |
| Total clubs required for league launch | 80 clubs |
| MCD clubs (already included) | 12 clubs (one per zone) |
| Non-MCD clubs to be onboarded | 68 clubs (272 teams) |
| Total non-MCD schools in Delhi-NCR (target universe) | 2,500+ schools |

### 2.2 Onboarding Philosophy

The onboarding of non-MCD clubs will be driven through official government channels rather than direct cold outreach. This ensures:

| Benefit | Explanation |
| --- | --- |
| Credibility | Schools trust government notices more than private outreach |
| Reach | MCD/DoE has access to every school in Delhi-NCR |
| Speed | One official notice reaches thousands of schools instantly |
| Compliance | Schools are more likely to respond to government directives |
| Cost-effectiveness | No expensive door-to-door sales team required |

### 2.3 Four-Pronged Onboarding Approach

| Layer | Issuing Authority | Target Audience | Purpose |
| --- | --- | --- | --- |
| Layer 1 | MCD (Education Department) | 1,512 MCD schools | Form 12 MCD clubs; inform MCD schools |
| Layer 2 | Delhi Government (DoE) – if required | All non-MCD schools (govt & private) in Delhi | Onboard 68 non-MCD clubs |
| Layer 3 | AIFF (All India Football Federation) | Football-playing schools, academies, coaches | Endorsement + football-specific outreach |
| Layer 4 | DCA (Delhi Cricket Association) | Cricket-playing schools, academies, coaches | Endorsement + cricket-specific outreach |

## 3. Notices – MCD & Delhi Government (DoE)

### 3.1 Notice Strategy Overview

| Notice Type | When to Use | Target | Content Focus |
| --- | --- | --- | --- |
| MCD Notice | Primary notice – always issued | MCD schools + all schools (via MCD's network) | League launch, MCD clubs, talent identification |
| Delhi Government (DoE) Notice | If required – issued in parallel or after MCD notice | All government & private non-MCD schools | Broader reach, mandatory compliance for govt schools |

### 3.2 MCD Notice – Sample Content

MCD LETTERHEAD

MUNICIPAL CORPORATION OF DELHI
Education Department

No. MCD/Edn/MML/2025-26/_______ Dated: _______

CIRCULAR TO ALL SCHOOLS UNDER MCD & ALL RECOGNIZED SCHOOLS IN DELHI-NCR

SUBJECT: Launch of MCD Mini League (Football & Cricket) for Grassroots Talent Identification – U-9 & U-11 Boys & Girls

To,
All Principals / School Heads
MCD Schools (1,512 schools) & All Recognized Schools (Government & Private) under DoE Delhi

Dear Principal,

The Municipal Corporation of Delhi (MCD), in partnership with Khelo Tech & Strategy Pvt. Ltd., is pleased to announce the launch of the MCD Mini League (MML) – a flagship grassroots sports initiative for the children of Delhi.

1. Core Objective – Grassroots Talent Identification

The primary motive of this league is to identify and nurture grassroots-level sporting talent across Delhi-NCR. Through structured competition and digital tracking, the league aims to discover young athletes, create digital talent profiles, and build a sustainable sporting pipeline from the grassroots upward.

2. League Details

| Parameter | Details |
| --- | --- |
| Sports | Football & Cricket |
| Age Categories | Under-9 & Under-11 |
| Gender | Boys & Girls |
| League Structure | 4-tier pyramid (Bronze → Silver → Gold → Diamond) with promotion & relegation |
| Technology Platform | Centralized Game Management System (GMS) for digital registration, match management, and talent scouting |

3. Club Formation – Two Options for Schools

Schools may participate by forming or joining a club as per the following options:

| Option | Description | Best For |
| --- | --- | --- |
| Option A: Single-School Club | A single school forms its own club and fields all 4 teams (U-9 Boys, U-9 Girls, U-11 Boys, U-11 Girls) | Large schools with 500+ students and sufficient player strength |
| Option B: Multi-School Cluster | 2-3 schools come together to form a joint club, pooling players across schools | Small or medium schools that cannot field all teams independently |

4. MCD Clubs (Pre-Formed)

Twelve (12) MCD clubs have already been formed, one club per MCD zone. These clubs represent MCD schools and will participate at zero registration fee (CSR-subsidized).

5. Registration for Non-MCD Clubs

| Particulars | Details |
| --- | --- |
| Registration Fee | ₹25,000 per sport (Football OR Cricket) per club |
| Fee for Both Sports | ₹50,000 per club |
| Last Date for Registration | [Date] |
| Mode of Registration | Online via GMS portal: [link] |
| Documents Required | School recognition certificate, Club Manager nomination, coaching staff details, Code of Conduct undertaking |

6. Support for Cluster Formation

Schools that cannot form a club independently will be facilitated by Khelo Tech to form clusters with nearby schools. Cluster facilitation requests can be submitted through the GMS portal.

7. External Club Supervision

To ensure transparency and avoid conflict of interest, each club will be assigned an external, neutral club supervisor (not a coach, parent, or school teacher). Details of the supervisor role and appointment process are attached as Annexure A.

8. Important Dates

| Activity | Date |
| --- | --- |
| Release of this notice | [Date] |
| Last date for registration intent | [Date] |
| Last date for player registration | [Date] |
| League start date | [Date] |

9. Contact for Queries

For any queries regarding registration, cluster formation, or league operations, please contact:

- MCD Nodal Officer: [Name, Phone, Email]

- Khelo Tech Support: [Phone, Email, GMS portal link]

Sd/-
Commissioner
Municipal Corporation of Delhi

Sd/-
Director (Education)
Municipal Corporation of Delhi

Copy to:

- All Zone Coordinators – for dissemination

- Khelo Tech & Strategy Pvt. Ltd. – for implementation

- AIFF & DCA – for information and endorsement

- Director of Education, Delhi – for information

## 3.4 When to Use Which Notice

| Scenario | Action |
| --- | --- |
| Default scenario | MCD notice is sufficient to reach MCD schools + non-MCD schools (via MCD's network) |
| If non-MCD schools do not respond adequately | Issue DoE notice as follow-up reinforcement |
| If Delhi Government schools (DoE) need mandatory directive | Issue DoE notice with stronger language |
| If league needs maximum visibility and government backing | Issue BOTH notices simultaneously |
| If league is expanded beyond MCD's jurisdiction | DoE notice becomes primary |

## 4. Involvement of AIFF & Delhi Cricket Association (DCA)

### 4.1 Why Involve AIFF & DCA?

| Benefit | Explanation |
| --- | --- |
| Credibility | Official endorsements from national/state sports federations add immense credibility |
| Reach | AIFF and DCA have direct access to football and cricket playing schools, academies, and coaches |
| Talent Pathway | AIFF and DCA can use the league as a feeder for their grassroots and age-group programs |
| Coach Validation | AIFF and DCA can help verify coach qualifications and provide training |
| Easier Onboarding | Schools that are already affiliated with AIFF or DCA will trust and join the league faster |

### 4.2 Role of AIFF

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Issue endorsement circular to all AIFF-affiliated members in Delhi-NCR | Week 1 | AIFF Grassroots Dept |
| Share MML registration link on AIFF website and social media | Week 1 | AIFF Communications |
| Allow AIFF-affiliated coaches to get recognition for participating | Ongoing | AIFF Coaching Dept |
| Consider MML as a recognized grassroots league for talent identification | Season 2 onward | AIFF |

### 4.3 Role of Delhi Cricket Association (DCA)

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Issue endorsement circular to all DCA-affiliated schools and clubs in Delhi-NCR | Week 1 | DCA Secretary |
| Share MML registration link on DCA website and social media | Week 1 | DCA Communications |
| Provide input on age-appropriate cricket formats (U-9 & U-11) | Pre-launch | DCA Technical Committee |
| Allow DCA-registered coaches to participate as club coaches | Ongoing | DCA |

## 5. Club Formation Basis: Single-School vs. Multi-School Clusters

### 5.1 Guiding Principle

A club in the MCD Mini League must field 4 teams per sport:

- U-9 Boys

- U-9 Girls

- U-11 Boys

- U-11 Girls

Minimum players required: 8 players per team (flexible for inaugural season) → 32 players minimum per club per sport.
Ideal players per club: 12-15 players per team → 48-60 players per club per sport.

### 5.2 Club Formation Decision Matrix

| School Capacity (Approx. student strength) | Recommended Club Type | Action Required |
| --- | --- | --- |
| 1,000+ students | Single-school club | Register independently on GMS |
| 500-1,000 students | Single-school club (possible) OR 2-school cluster | Attempt independent; if insufficient players, request a cluster. |
| 250-500 students | 2-school cluster | Must find 1 partner school (Khelo Tech will facilitate) |
| 100-250 students | 3-school cluster | Must find 2-3 partner schools (Khelo Tech will facilitate) |
| Below 100 students | Not eligible as a leader; join existing club | Cannot form own club; must join nearby club as participating school |

### 5.3 Examples of Club Formation Scenarios

| Scenario | Club Type | Example | How It Works |
| --- | --- | --- | --- |
| Large school wants its own identity | Single-school club | "DPS RK Puram Club" | DPS RK Puram fields all 4 teams (U-9/U-11 Boys/Girls) independently from its own students |
| Two medium schools combine | Joint cluster (2 schools) | "South Delhi United Club" | School A (boys stronger) + School B (girls stronger) combine to form a complete club |
| Three small schools combine | Micro cluster (3 schools) | "Model Town Colts Club" | 3 small budget private schools each contribute 10-12 players to form 4 teams |
| Boys-only school | Special cluster | "North Delhi Lions Club" | Boys-only school partners with nearby girls' school to field girls' teams |
| School has only primary section | Partial cluster | "Civil Lines Junior Club" | School has U-9 but not U-11; partners with another school for U-11 |

### 5.4 Cluster Facilitation by Khelo Tech

| Step | Action | Responsible |
| --- | --- | --- |
| 1 | School registers intent on GMS and checks "Need cluster partner" | School principal |
| 2 | Khelo Tech identifies nearby schools (within 3 km radius) with similar need | Zone Operations Lead |
| 3 | Introduction call/meeting arranged between schools | Relationship Manager |
| 4 | Cluster agreement template provided and signed | Schools + Khelo Tech witness |
| 5 | One Club Manager nominated from one of the schools (rotating basis, annually) | Schools mutually decide |
| 6 | Cluster registered as a single club on GMS | Club Manager |

### 5.5 Cluster Agreement Template (Simplified)

CLUSTER AGREEMENT FOR MCD MINI LEAGUE

This agreement is made on [Date] between:

1. [School A Name], represented by [Principal Name]

2. [School B Name], represented by [Principal Name]

3. [School C Name], represented by [Principal Name] (if applicable)

Hereby agree to form a joint club named: "[Cluster Name] Club"

Terms:

1. Players will be drawn from all participating schools

2. Club Manager will be nominated from [School Name] for this season (rotates annually)

3. Registration fee of ₹25,000 per sport will be shared as per mutual agreement

4. Practice venue will rotate between schools on a weekly basis

5. Any dispute between schools will be resolved by MCD Zone Coordinator

6. Each school will provide at least one coach or support staff

Signatures:

_________________ (School A)

_________________ (School B)

_________________ (School C)

Witnessed by:

_________________ (Khelo Tech Representative)

_________________ (MCD Zone Coordinator)

### 5.6 Rules for Naming Clubs

| Club Type | Naming Convention | Examples |
| --- | --- | --- |
| Single-school club | "[School Name] Club" | "DPS RK Puram Club", "Springdales Club" |
| Joint cluster (2 schools) | "[School A Initials]-[School B Initials] Club" OR chosen name | "RK-PS Club", "North Delhi United" |
| Micro cluster (3+ schools) | "[Zone Name] [Chosen Name] Club" | "Civil Lines Champions Club", "Rohini Eagles" |

Note: Club names must be approved by Zone Coordinator to avoid duplication, offensive names, or brand conflicts.

## 6. Registration Workflow (Step-by-Step)

### 6.1 Overall Registration Flow

MCD/DoE Notice Issued → School receives notice → School visits GMS portal → School submits intent → School chooses club type (single/cluster) → Documents uploaded → Fee paid (non-MCD) → Zone Coordinator verification → Club approved → Player registration begins → Teams formed → Onboarding complete

### 6.2 Step-by-Step Registration Process

| Step | Action | Responsible | Timeline | System Status |
| --- | --- | --- | --- | --- |
| 1 | School receives MCD/DoE notice and visits GMS portal | School principal | Week 1 | N/A |
| 2 | School submits intent to participate (online form) | School principal | Week 1-2 | "Intent Received" |
| 3 | School selects club type: Single-school OR Request cluster | School principal | Week 2 | "Club Type Selected" |
| 4 | If cluster requested – Khelo Tech facilitates pairing | Zone Operations Lead | Week 2-3 | "Cluster Formation in Progress" |
| 5 | Club profile created on GMS (by school or by Khelo Tech) | Club Manager | Week 2-3 | "Profile Created" |
| 6 | Documents uploaded (school recognition, manager nomination, coach details, code of conduct) | Club Manager | Week 3 | "Documents Uploaded" |
| 7 | Registration fee paid (non-MCD clubs only) | Club Manager | Week 3 | "Payment Received" |
| 8 | Zone Coordinator verifies all documents | Zone Coordinator | Week 3-4 | "Under Review" → "Approved" |
| 9 | Club Manager begins player registration (upload player names, age proofs) | Club Manager | Week 4-5 | "Player Registration Open" |
| 10 | Teams formed (U-9 Boys, U-9 Girls, U-11 Boys, U-11 Girls) | Club Manager | Week 5 | "Teams Formed" |
| 11 | Onboarding complete – club ready for league | System | Week 5 | "Ready for League" |

### 6.3 Registration Fee Structure (Non-MCD Clubs Only)

| Participation Option | Football Only | Cricket Only | Both Sports |
| --- | --- | --- | --- |
| Standard Registration | ₹25,000 | ₹25,000 | ₹50,000 |

MCD Clubs: Zero registration fee (CSR subsidized)

Payment Methods: Online transfer (UPI, Net Banking, Credit/Debit Card), NEFT/RTGS, Demand Draft

## 7. Verification Process

### 7.1 Verification Layers

| Layer | Verifier | What is Verified | Timeline | Outcome |
| --- | --- | --- | --- | --- |
| Layer 1 – System | GMS automated | Document format, mandatory fields, age format, duplicate entries | Instant | Pass/Fail with error list |
| Layer 2 – Zone | MCD Zone Coordinator | School authenticity, zone alignment, cluster validity, document genuineness | 48 hours | Approved / Action Required / Rejected |
| Layer 3 – Central | League Director | Fee confirmation (non-MCD), special cases, dispute resolution | 24 hours | Final approval |
| Layer 4 – Spot | External Club Supervisor | On-match-day age verification, school affiliation | Throughout season | Pass/Refer |

### 7.2 Age Verification Protocol (Critical for U-9 & U-11)

| Step | Action | Responsible | Document Accepted |
| --- | --- | --- | --- |
| 1 | Upload age proof during player registration | Club Manager | Birth certificate / Aadhaar / School leaving certificate |
| 2 | GMS automated date check (validates age against cutoff) | System | N/A |
| 3 | Zone Coordinator reviews flagged players | Zone Coordinator | The original document may be requested |
| 4 | Random spot check at matches (10% of players) | External Club Supervisor | Original document required |
| 5 | Disputed case escalation | League Director | Medical/age certificate from authorized hospital |

### 7.3 Verification Outcomes

| Status | Meaning | Next Action | Timeline |
| --- | --- | --- | --- |
| Approved | Club meets all criteria | Proceed to player registration | Immediate |
| Action Required | Missing documents or errors | Resubmit corrected documents | Within 5 calendar days |
| Rejected | Does not meet eligibility criteria | Appeal to League Director | Within 7 calendar days |

## 8. External Club Supervisor – Role, Eligibility & Appointment

### 8.1 The Problem – Conflict of Interest

If a coach, parent, or school teacher is appointed as club manager or supervisor, the following conflicts arise:

| Conflict | Example |
| --- | --- |
| Coach as manager | Coach may select only "his" favorite players, ignore merit |
| Parent as manager | Parent may favor their own child or create team politics |
| School teacher as manager | Teacher may prioritize their own school's students over others in a cluster |
| Principal as manager | The principal may not have time; also, they may be biased toward their own school |

### 8.2 The Solution – External, Neutral Club Supervisor

Each club (whether single-school or cluster) will have an external club supervisor who is:

| Criteria | Requirement |
| --- | --- |
| Not a coach | Cannot be the same person as the head coach or any assistant coach |
| Not a parent | Cannot be a parent of any player in the club |
| Not a teacher from participating schools | For clusters, cannot be employed by any school in the cluster |
| Not a school principal | No conflict of interest at school leadership level |
| Not a current MCD employee | To avoid favoritism toward MCD clubs |

### 8.3 Who Can Be an External Club Supervisor?

The following individuals are eligible to be Club Supervisors:

| Eligible Person | Source | How to Onboard |
| --- | --- | --- |
| Retired government sports officer | MCD/DoE/Sports Authority of India retired staff | Empaneled list maintained by Khelo Tech |
| Physical Education college graduate () | Delhi University, IGIPESS, Lakshmibai College | Recruitment drive |
| NIS certified coach (not actively coaching) | Netaji Subhas Natunemployedional Institute of Sports | Short-term contract |
| NCC / Scout & Guide officer (retired or active, with permission) | NCC units across Delhi | Permission letter required |
| MBA / Sports Management graduate | University placement cells | Paid position |
| Retired army / paramilitary officer (sports background) | Ex-servicemen organizations | Honorarium |

### 8.4 Who Is NOT Eligible (Conflict of Interest)

| Ineligible Person | Reason |
| --- | --- |
| Head coach or assistant coach of the same club | Cannot supervise own decisions |
| Parent of any player in the club | Bias toward own child |
| Teacher or staff of any school in the club (for clusters) | Bias toward own school |
| Principal of any school in the club | Conflict of interest |
| MCD employee | Potential favoritism |
| Relative of any player | Family bias |

### 8.5 Role & Responsibilities of External Club Supervisor

| Responsibility | Frequency | Description |
| --- | --- | --- |
| Registration oversight | One-time | Ensure all player registrations are complete, age proofs uploaded |
| Attendance verification | Match-day | Verify player attendance independently (not relying only on the coach). |
| Conflict resolution (internal) | As needed | Resolve disputes between players, parents, or coaches within the club |
| Match-day conduct monitoring | Every match | Ensure coaches and players follow code of conduct |
| Communication with MCD | Weekly | Report any issues to Zone Coordinator |
| Financial transparency (non-MCD clubs) | Monthly | Oversee collection and use of club funds (if any) |
| Child safety compliance | Ongoing | Ensure all coaches have background checks, report any concerns |
| Parent grievance collection | Ongoing | Anonymous feedback from parents to be shared with MCD |

### 8.6 How External Club Supervisors Are Appointed

| Step | Action | Responsible |
| --- | --- | --- |
| 1 | Khelo Tech maintains a central empaneled list of eligible supervisors | Khelo Tech HR + MCD |
| 2 | Club applies for a supervisor via GMS (after club registration) | Club Manager |
| 3 | Khelo Tech assigns a supervisor from the empaneled list (randomized, zone-wise) | Zone Operations Lead |
| 4 | Supervisor is introduced to the club (virtual or in-person) | Zone Operations Lead |
| 5 | Supervisor signs a Code of Conduct and Conflict of Interest declaration | Supervisor + Khelo Tech |
| 6 | Supervisor receives GMS access (limited to view-only + reporting) | Technology Lead |

## 9. Zone-Level Monitoring System

### 9.1 Zone Monitoring Dashboard

Each of the 12 zones has a dedicated Zone Monitoring Dashboard on GMS.

| Role | Access Level |
| --- | --- |
| MCD Zone Coordinator | Full read/write (approvals, flags, comments) |
| Khelo Tech Zone Operations Lead | Full read/write (operational updates) |
| External Club Supervisor | View-only for assigned clubs |

### 9.2 Dashboard Metrics Tracked per Zone

| Metric | Data Source | Update Frequency |
| --- | --- | --- |
| Number of clubs registered (target 6-7 per zone) | GMS registration module | Real-time |
| Document completion % per club | Document upload tracker | Real-time |
| Player roster completeness | Player registration module | Real-time |
| Age verification status (% verified) | Age verification log | Real-time |
| External Supervisor assigned (yes/no) | Supervisor module | Real-time |
| Match attendance % | Attendance module | After each match |

## 10. Governance & Compliance Framework’

### 10.1 Regulatory Adherence

| Regulation / Policy | Relevance | Club Compliance Requirement |
| --- | --- | --- |
| MCD Education Department Scheme | Mandates talent scouting | Clubs must participate in talent identification |
| Khelo Bharat Niti 2025 | Grassroots sports culture | Clubs must promote participation |
| NEP 2020 | Sports as part of education | No child excluded due to fees |
| POCSO Act | Protection of minors | Background check for all club personnel |

### 10.2 Non-Compliance Consequences

| Non-Compliance Area | First Instance | Second Instance | Third Instance |
| --- | --- | --- | --- |
| Late registration | Warning + late fee | Fine doubled | Disqualification |
| Missing documents | 48-hour notice | Fine ₹5,000 | Temporary suspension |
| Age fraud (single player) | Player disqualification + club warning | Fine ₹25,000 | Club suspension |
| No External Supervisor appointed | Club not approved | N/A | N/A |
| Match no-show (unexcused) | 0-3 forfeit + fine ₹5,000 | Fine ₹10,000 + point deduction | Disqualification |

# WEBSITE – PART 1

# MCD MINI LEAGUE

# WEBSITE CONTENT DOCUMENT – PART 1

## Home Page | About the League | Clubs Ecosystem | Start a Club | Club Registration Guidelines | Club Rules & Regulations | Downloads | FAQ

# HOME PAGE

## HERO SECTION

### MCD MINI LEAGUE

### Building Delhi's Largest Community Sports Ecosystem

The MCD Mini League is a city-wide grassroots sports initiative dedicated to transforming the sporting landscape of Delhi through community participation, club development, athlete growth, and structured competition.

Designed to create sustainable sporting opportunities for children and young athletes, the league connects communities, clubs, coaches, volunteers, and institutions through a unified sports ecosystem that promotes participation, development, and excellence.

Through structured competitions, club-based training environments, athlete development programmes, and talent identification pathways, the MCD Mini League is building the foundation for the next generation of athletes while strengthening community engagement through sport.

#### CTA Buttons

- Register Now

- Explore Clubs

- View Fixtures

## SPORTS IMPACT ACROSS DELHI

### Creating Opportunities Through Sport

The MCD Mini League is committed to making sports accessible, inclusive, and impactful across Delhi. By supporting clubs, athletes, coaches, and volunteers, the league is creating opportunities that extend far beyond competition.

Our focus is on participation, development, leadership, and community engagement, ensuring that every athlete has access to meaningful sporting experiences.

#### Impact Statistics

- Community Sports Clubs

- Registered Athletes

- Participating Teams

- Sports Venues

- Matches Conducted

- Delhi Zones Covered

## MORE THAN A LEAGUE

### Building Communities Through Sport

The MCD Mini League is more than a sporting competition.

It is a movement designed to strengthen grassroots sports participation, develop athletes, empower communities, and promote healthy lifestyles.

By encouraging local engagement through community sports clubs and structured competitions, the league creates pathways for personal growth, social inclusion, and sporting excellence.

Every club formed, every athlete registered, and every match played contributes to a stronger and healthier sporting culture for Delhi.

#### CTA

Learn More

## COMMUNITY CLUBS NETWORK

### The Foundation of the League

Community Sports Clubs are the backbone of the MCD Mini League ecosystem.

These clubs provide year-round opportunities for participation, coaching, training, and competition while creating safe and supportive environments for athlete development.

Through a growing network of affiliated clubs, the league seeks to ensure that every community has access to quality sporting opportunities.

#### CTA

Explore Clubs

## SPORTS DEVELOPMENT PATHWAY

### The Athlete Journey

The MCD Mini League has been designed to support athletes at every stage of their sporting journey.

#### Development Pathway

Community Member

↓

Community Sports Club

↓

Structured Training

↓

Club Competitions

↓

MCD Mini League

↓

Talent Identification

↓

Advanced Development Opportunities

↓

Future Sporting Pathways

This structured model ensures that athletes receive continuous opportunities to learn, develop, compete, and progress.

## UPCOMING FIXTURES

### Upcoming Matches

Stay updated with the latest matches, schedules, and competition activities across all league categories.

Users will be able to view:

- Match Schedules

- Venue Details

- Team Information

- Competition Categories

- Results & Updates

#### CTA

View Full Schedule

## FEATURED ATHLETES

### Athletes to Watch

The MCD Mini League celebrates athletes who demonstrate dedication, sportsmanship, leadership, and excellence.

Featured athlete profiles will highlight achievements, performances, and development journeys, inspiring future generations to participate in sports.

#### Display Information

- Athlete Photograph

- Club Name

- Team

- Position

- Performance Statistics

- Recent Achievements

## NEWS & UPDATES

### Stay Connected

Follow the latest developments from across the MCD Mini League ecosystem.

Content includes:

- Match Reports

- Competition Updates

- Club Success Stories

- Athlete Features

- Community Events

- Announcements

- Development Programmes

#### CTA

View All News

## PARTNERS IN SPORTS DEVELOPMENT

### Supporting Grassroots Sports

The MCD Mini League is made possible through the support of government bodies, institutions, community organizations, and corporate partners committed to developing sports and empowering young athletes.

Partner Categories:

- Title Sponsor

- Co-Sponsors

- Official Partners

- Category Sponsors

- In-Kind Sponsors

- Strategic Partners

# ABOUT THE LEAGUE

## ABOUT MCD MINI LEAGUE

The MCD Mini League is a comprehensive grassroots sports initiative focused on increasing participation, improving access to sporting opportunities, and creating structured pathways for athlete development across Delhi.

The league has been established to strengthen community engagement through sports while building a sustainable framework that supports athlete growth, club development, coaching excellence, and competitive participation.

Through collaboration between communities, institutions, coaches, volunteers, and sporting organizations, the initiative aims to create a long-term impact on the sporting landscape of Delhi.

## OUR VISION

To create a vibrant, inclusive, and sustainable sports ecosystem that encourages participation, nurtures talent, and promotes healthy lifestyles through community-based sporting opportunities.

We envision a future where every child has access to quality sporting experiences and the opportunity to develop their potential through sport.

## OUR MISSION

Our mission is to:

- Promote grassroots sports participation.

- Strengthen community sports clubs.

- Develop future athletes.

- Encourage healthy lifestyles.

- Foster sportsmanship and leadership.

- Build stronger communities through sport.

- Create pathways for sporting excellence.

## OUR OBJECTIVES

The MCD Mini League seeks to:

- Increase access to sports.

- Encourage youth participation.

- Strengthen community clubs.

- Improve athlete development opportunities.

- Identify emerging talent.

- Promote social inclusion.

- Enhance community engagement.

- Create sustainable sports infrastructure.

## WHY SPORTS MATTER

Sport plays a vital role in physical, mental, emotional, and social development.

Participation in sports helps young people develop confidence, discipline, teamwork, leadership, resilience, and healthy lifestyles.

The MCD Mini League uses sport as a platform to inspire positive change while creating opportunities that benefit athletes, families, schools, and communities.

### Key Impact Areas

- Health & Wellness

- Youth Development

- Leadership Development

- Community Engagement

- Social Inclusion

- Talent Identification

# CLUBS ECOSYSTEM

## COMMUNITY SPORTS CLUBS

### The Foundation of the MCD Mini League

Community Sports Clubs form the backbone of the MCD Mini League ecosystem.

These clubs create local opportunities for participation, training, competition, and athlete development while strengthening social connections within communities.

Every affiliated club contributes to building a stronger sporting culture across Delhi.

## WHY COMMUNITY CLUBS MATTER

Community clubs play a critical role in:

- Athlete Development

- Community Engagement

- Talent Identification

- Leadership Development

- Volunteer Participation

- Inclusive Sporting Opportunities

By creating local access to sports, clubs become powerful drivers of positive community change.

## BENEFITS OF JOINING A CLUB

### For Athletes

- Regular Competition

- Skill Development

- Talent Recognition

- Team Experience

### For Parents

- Safe Sporting Environment

- Development Opportunities

- Positive Social Engagement

- Health & Fitness Benefits

### For Communities

- Increased Participation

- Community Pride

- Stronger Social Connections

- Volunteer Opportunities

## CLUB DIRECTORY

Visitors can search and discover affiliated clubs based on:

- Zone

- Ward

- Sport

- Age Group

- Location

Each club profile includes:

- Club Overview

- Sports Offered

- Contact Information

# START A CLUB

## START A COMMUNITY SPORTS CLUB

### Build Sporting Opportunities in Your Community

Community Sports Clubs are essential to expanding participation and creating opportunities for athletes across Delhi.

Individuals, institutions, schools, organizations, academies, and community groups are encouraged to establish affiliated clubs and become part of the MCD Mini League ecosystem.

Creating a club enables communities to provide structured sporting opportunities while contributing to a larger movement focused on youth development and healthy lifestyles.

## WHO CAN APPLY?

Applications are welcome from:

- Resident Welfare Associations

- Schools

- Colleges

- Universities

- Sports Academies

- NGOs

- Registered Societies

- Trusts

- Community Groups

- Individual Promoters

## BENEFITS OF AFFILIATION

Affiliated clubs gain access to:

- League Participation

- Athlete Development Programmes

- Club Recognition

- Talent Identification Opportunities

- Development Resources

- Workshops & Training

- Community Network Support

- Promotional Opportunities

## REQUIRED CLUB STRUCTURE

Each affiliated club must have a basic governance framework including:

- President

- Secretary

- Proctor

- Treasurer

- Club Coordinator

This structure ensures transparency, accountability, and effective club management.

# CLUB REGISTRATION GUIDELINES

## ELIGIBILITY REQUIREMENTS

To qualify for affiliation, applicants must:

- Demonstrate a commitment to sports development.

- Maintain a basic governance structure.

- Support inclusive participation.

- Provide safe sporting environments.

- Comply with league regulations.

- Maintain athlete records.

## REQUIRED DOCUMENTS

### Identity Documents

- Government-issued ID

- Address Proof

### Organizational Documents

- Registration Certificate (if applicable)

- Constitution/Bylaws (if applicable)

### Infrastructure Documents

- Venue Details

- Facility Information

- Ground Availability Information

- Usage Permissions

### Administrative Documents

- Office Bearer Details

- Contact Information

- Authorization Letters

## AFFILIATION PROCESS

### Step 1 – Review Guidelines

Understand club eligibility requirements and responsibilities.

### Step 2 – Prepare Documentation

Gather all required documents and supporting information.

### Step 3 – Submit Application

Complete the online application form and upload required documents.

### Step 4 – Verification

The submitted information will be reviewed by the affiliation team.

### Step 5 – Approval

Eligible clubs will receive affiliation approval.

### Step 6 – Activation

The club became an active member of the MCD Mini League ecosystem.

# CLUB RULES & REGULATIONS

## GOVERNANCE REQUIREMENTS

Affiliated clubs must operate in a transparent, responsible, and professional manner.

Clubs are expected to maintain accurate records, follow established procedures, and uphold the values of the MCD Mini League.

## ATHLETE PROTECTION STANDARDS

Every affiliated club must:

- Provide safe sporting environments.

- Promote athlete welfare.

- Prevent harassment and discrimination.

- Encourage fair play.

- Ensure equal participation opportunities.

- Follow safeguarding guidelines.

## ADMINISTRATIVE REQUIREMENTS

Clubs must:

- Maintain membership records.

- Maintain athlete databases.

- Submit information when requested.

- Comply with competition regulations.

- Cooperate during audits and reviews.

## CODE OF CONDUCT

All club representatives must demonstrate:

- Integrity

- Respect

- Fair Play

- Professionalism

- Accountability

- Sportsmanship

Any conduct that damages the reputation of the league or violates league regulations may result in disciplinary action.

# DOWNLOADS

## RESOURCE CENTRE

The Downloads Centre provides essential documents, templates, policies, and guidelines for clubs, athletes, coaches, volunteers, and stakeholders.

### Available Downloads

- Club Registration Handbook

- Club Formation Guidelines

- Club Constitution Template

- Affiliation Regulations

- Code of Conduct

- Safeguarding Guidelines

- Branding Guidelines

- Competition Regulations

- Registration Forms

# FREQUENTLY ASKED QUESTIONS

## What is the MCD Mini League?

The MCD Mini League is a grassroots sports initiative designed to promote participation, athlete development, club growth, and community engagement through structured sporting opportunities.

## Who can participate?

Children and young athletes who meet the eligibility requirements established for the respective competition categories.

## How do I join a club?

You can browse the Club Directory and contact an affiliated club directly to inquire about membership and participation opportunities.

## Can I start my own club?

Yes. Schools, RWAs, academies, NGOs, societies, community groups, and individuals may apply for club affiliation subject to eligibility requirements.

## Is there a club registration fee?

Details regarding affiliation and registration fees will be published in the official registration guidelines.

## What documents are required for affiliation?

Applicants are generally required to submit identity documents, organizational documents, infrastructure details, and governance information.

## How are athletes selected for competitions?

Athletes participate through affiliated clubs and are registered according to the competition regulations applicable to their category.

## How can organizations become partners?

Organizations can explore sponsorship and partnership opportunities through the Sponsors & Partners section of the website or contact the partnership team directly.

## Where can I find official rules and guidelines?

All official policies, regulations, and resource materials are available in the Downloads section.

# WEBSITE - PART 2

# MCD MINI LEAGUE

# WEBSITE CONTENT DOCUMENT – PART 2

## Tournament | Teams | Athletes | Fixtures & Results | Standings | Venues

# TOURNAMENT

## TOURNAMENT OVERVIEW

### Structured Competition. Meaningful Development.

The MCD Mini League competition framework has been designed to provide athletes and clubs with structured, age-appropriate, and competitive sporting experiences.

The tournament serves as a platform where athletes can apply their training, develop match experience, build confidence, and showcase their abilities in a professional and organized environment.

More than determining winners, the competition is focused on athlete development, fair play, teamwork, and continuous improvement.

## TOURNAMENT OBJECTIVES

The competition framework aims to:

- Promote regular participation in sports.

- Encourage healthy competition.

- Develop technical and tactical skills.

- Support athlete progression.

- Strengthen community club engagement.

- Create opportunities for talent identification.

- Foster sportsmanship and leadership.

## LEAGUE STRUCTURE

### A Progressive Competition Model

The MCD Mini League follows a structured league system designed to encourage continuous growth and performance.

#### Diamond League

The highest competitive tier featuring top-performing teams and athletes.

#### Gold League

A competitive platform for clubs demonstrating strong performance and development.

#### Silver League

A developmental competition tier supporting emerging clubs and athletes.

#### Bronze League

An entry-level competition platform focused on participation, learning, and development.

This structure ensures that clubs and athletes compete at appropriate levels while providing opportunities for progression.

## COMPETITION FORMAT

### Group Stage

Teams compete in a round-robin format within their respective groups.

Each team plays multiple matches, ensuring maximum participation and development opportunities.

### Knockout Stage

Top-performing teams from the group stage advance to the knockout rounds.

The knockout stage introduces higher levels of competition and performance pressure.

### Semi-Finals

Qualified teams compete for a place in the championship match.

### Final

The top teams compete for the championship title in their respective competition category.

## TOURNAMENT VALUES

### Fair Play

Respect for opponents, officials, teammates, and the game.

### Inclusion

Providing equal opportunities for participation.

### Development

Prioritizing athlete growth and learning.

### Excellence

Encouraging continuous improvement and achievement.

### Community

Strengthening relationships through sport.

## RULES & REGULATIONS

### Competition Governance

All competitions are conducted in accordance with official league regulations and approved competition policies.

### Athlete Eligibility

Participants must:

- Meet age-category requirements.

- Be registered through an affiliated club.

- Complete registration procedures.

- Meet verification requirements.

### Team Registration

Teams must:

- Be affiliated with a registered club.

- Submit player rosters.

- Comply with competition regulations.

- Meet participation deadlines.

### Discipline & Conduct

Participants must demonstrate:

- Respect

- Sportsmanship

- Professional Conduct

- Fair Competition

Disciplinary procedures may be applied for misconduct or rule violations.

# TEAMS

## TEAM DIRECTORY

### Discover Participating Teams

The Team Directory showcases all teams participating in the MCD Mini League.

Visitors can explore team information, performance statistics, player profiles, and club affiliations.

### Team Information

Each team profile includes:

- Team Name

- Team Logo

- Club Affiliation

- Coach

- Captain

- Category

- Zone

- Season Statistics

### Team Search Filters

Visitors can search teams based on:

- Club

- Zone

- Competition Category

- League Division

- Age Group

## TEAM PROFILE PAGE

### Team Overview

The Team Profile provides a comprehensive overview of each participating team.

### Team Information

- Team Name

- Club Name

- League Category

- Home Venue

- Coach

- Captain

- Team Manager

### Team Statistics

Display:

- Matches Played

- Wins

- Draws

- Losses

- Goals Scored

- Goals Conceded

- Goal Difference

- Points

### Team Squad

Display:

- Player Photograph

- Player Name

- Position

- Jersey Number

- Category

### Season Performance

Track team performance throughout the season through detailed statistics and competition results.

### Fixtures & Results

View:

- Upcoming Matches

- Completed Matches

- Match Reports

- Team Performance Trends

# ATHLETES

## ATHLETE DIRECTORY

### Celebrating Every Athlete

The Athlete Directory showcases registered athletes participating across the MCD Mini League ecosystem.

The directory allows visitors to discover athletes, follow their progress, and learn about their sporting journeys.

### Search Athletes By

- Name

- Club

- Team

- Category

- Position

- Zone

### Athlete Listing Information

Each athlete profile preview includes:

- Photograph

- Athlete Name

- Club

- Team

- Position

- Competition Category

## ATHLETE PROFILE PAGE

### Athlete Overview

Each athlete profile serves as a digital sporting record highlighting participation, achievements, and development.

### Athlete Information

- Full Name

- Photograph

- Club

- Team

- Age Category

- Position

- Playing Number

### Athlete Statistics

Display:

- Matches Played

- Goals/Points

- Assists

- Clean Sheets

- Awards

- Performance Ratings

### Athlete Achievements

Showcase:

- Tournament Awards

- Team Recognition

- Leadership Roles

- Development Milestones

### Athlete Development Journey

Highlight:

- Club Participation

- Training Progress

- Competition Experience

- Talent Identification Opportunities

### Athlete Gallery

Display photographs and competition highlights.

# FIXTURES & RESULTS

## FIXTURES

### Stay Updated with Upcoming Matches

The Fixtures section provides athletes, coaches, clubs, parents, and supporters with access to upcoming competition schedules.

### Match Information

Display:

- Match Date

- Match Time

- Venue

- Team Names

- Competition Category

- League Tier

### Search & Filter

Visitors can filter fixtures by:

- Date

- Venue

- Team

- Club

- League

- Category

### Calendar View

Monthly competition calendar with scheduled matches.

### List View

Chronological list of all upcoming fixtures.

## RESULTS

### Match Results & Performance Updates

The Results section provides comprehensive information about completed matches.

### Results Information

Display:

- Final Score

- Match Summary

- Goals/Points Scorers

- Key Statistics

- Athlete of the Match

### Match Reports

Each completed match includes a detailed report covering:

- Match Overview

- Key Moments

- Team Performance

- Athlete Highlights

- Competition Impact

### Athlete of the Match

Recognizing outstanding individual performances that contribute positively to team success and sporting excellence.

# STANDINGS

## LEAGUE TABLES

### Track Team Performance

The Standings section provides real-time league rankings across all competition categories.

Teams are ranked based on competition rules and season performance.

### Table Information

Display:

Position

Team

Played

Won

Drawn

Lost

Goals For

Goals Against

Goal Difference

Points

### Competition Filters

Visitors can view standings based on:

- League Tier

- Age Category

- Competition Group

- Zone

### Performance Insights

Additional information may include:

- Recent Form

- Home Record

- Away Record

- Goals Statistics

- Progression Status

### Promotion & Advancement

Standings may influence qualification, advancement, and progression opportunities within the league structure.

# VENUES

## SPORTS VENUES DIRECTORY

### Discover Competition Venues

The Venues section provides information about the facilities used for MCD Mini League activities and competitions.

Each venue has been selected to support safe, accessible, and high-quality sporting experiences.

### Venue Information

Display:

- Venue Name

- Address

- Contact Information

- Location Map

- Accessibility Information

### Facilities Available

Venue profiles may include:

- Playing Fields

- Practice Areas

- Seating Facilities

- Washrooms

- Drinking Water

- Parking Areas

- Medical Support Facilities

### Venue Gallery

Photographs showcasing:

- Playing Areas

- Spectator Areas

- Facilities

- Accessibility Features

### Directions & Accessibility

Integrated map functionality allows visitors to:

- View Venue Location

- Get Directions

- Plan Travel Routes

- Check Accessibility Information

## HOSTING OPPORTUNITIES

### Become a Host Venue

Schools, institutions, sports complexes, academies, and community organizations interested in hosting MCD Mini League activities may apply to become approved venues.

Benefits include:

- Community Engagement

- Sports Promotion

- Increased Visibility

- Event Participation Opportunities

- Contribution to Grassroots Sports Development

## SAFETY & FACILITY STANDARDS

All approved venues are expected to maintain standards relating to:

- Athlete Safety

- Accessibility

- Playing Surface Quality

- Emergency Preparedness

- Crowd Management

- Facility Maintenance

These standards help ensure a positive and safe experience for all participants and visitors.

# WEBSITE - PART 3

# MCD MINI LEAGUE

# WEBSITE CONTENT DOCUMENT – PART 3

## Media Centre | Sponsors & Partners | Registration | Contact Us | Footer | Privacy Policy | Terms & Conditions | Code of Conduct | Safeguarding Policy

# MEDIA CENTRE

## MEDIA CENTRE OVERVIEW

### Stories, Achievements & Community Impact

The Media Centre serves as the official source for news, stories, announcements, photographs, videos, and updates from across the MCD Mini League ecosystem.

Through engaging content, the platform highlights athlete achievements, club development initiatives, community participation, competitions, and the broader impact of grassroots sports across Delhi.

Whether you are a parent, athlete, coach, volunteer, media representative, or sports enthusiast, the Media Centre provides a comprehensive view of the league's activities and achievements.

## NEWS

### Latest News & Announcements

Stay informed about the latest developments within the MCD Mini League.

Content Categories:

- League Announcements

- Competition Updates

- Club Features

- Athlete Stories

- Coach Spotlights

- Volunteer Recognition

- Community Initiatives

- Partnership Announcements

- Event Coverage

- Development Programmes

Each article will include:

- Featured Image

- Publication Date

- Category

- Author

- Related Articles

## GALLERY

### Capturing Moments That Matter

The Gallery showcases memorable moments from competitions, club activities, community events, training programmes, and athlete development initiatives.

Categories:

- Match Day Action

- Club Activities

- Community Sports Festivals

- Athlete Development Programmes

- Award Ceremonies

- Volunteer Activities

- Coaching Workshops

- Partner Activations

The gallery serves as a visual celebration of participation, achievement, and community engagement.

## VIDEOS

### Bringing the Action to Life

The Video Library features dynamic content from across the MCD Mini League ecosystem.

Video Categories:

- Match Highlights

- Athlete Interviews

- Coach Interviews

- Club Stories

- Community Impact Stories

- Event Recaps

- Promotional Films

- Behind-the-Scenes Features

- Talent Showcase Videos

- Partner Features

## PRESS & MEDIA

### Official Media Resources

The Media Centre provides accredited media representatives with access to official resources and information.

Resources Include:

- Press Releases

- Media Kits

- Official Logos

- Brand Guidelines

- High-Resolution Images

- Fact Sheets

- Event Information

Media inquiries can be directed through the Contact section of the website.

# SPONSORS & PARTNERS

## OVERVIEW

### Partnering for Community Impact

The MCD Mini League is built through collaboration.

Our partners play a critical role in helping us expand participation, strengthen community clubs, support athlete development, and create sustainable sporting opportunities across Delhi.

Through strategic partnerships, sponsorships, and community support, we are collectively investing in the future of grassroots sports.

## WHY PARTNER WITH MCD MINI LEAGUE?

### Meaningful Community Engagement

The MCD Mini League provides organizations with an opportunity to create measurable social impact through youth development, community engagement, and grassroots sports participation.

### Extensive Community Reach

Connect directly with:

- Athletes

- Parents

- Coaches

- Volunteers

- Community Leaders

- Educational Institutions

- Sports Clubs

### Strong Brand Visibility

Sponsors receive visibility through:

- Website Branding

- Event Branding

- Venue Branding

- Digital Campaigns

- Community Programmes

- Competition Assets

### Long-Term Impact

Partnerships contribute directly to:

- Sports Development

- Youth Empowerment

- Community Building

- Talent Identification

- Healthy Lifestyle Promotion

## SPONSORSHIP CATEGORIES

### Title Sponsor

The premier sponsorship category with maximum visibility and recognition across all league assets.

### Co-Sponsor

Strategic partners supporting the league's objectives while receiving significant branding and engagement opportunities.

### Official Partner

Organizations officially associated with the MCD Mini League ecosystem.

### Category Sponsor

Exclusive sponsorship within a designated sector or category.

Examples:

- Banking Partner

- Education Partner

- Healthcare Partner

- Technology Partner

- Equipment Partner

- Nutrition Partner

### In-Kind Sponsor

Organizations contributing products, services, infrastructure, technology, or operational support.

## BECOME A PARTNER

Organizations interested in supporting grassroots sports development are invited to connect with the MCD Mini League partnership team.

### CTA

Download Sponsorship Deck

Contact Partnership Team

Become a Partner

# REGISTRATION HUB

## REGISTRATION OVERVIEW

### Join the MCD Mini League Ecosystem

Whether you are an athlete, coach, volunteer, or community organization, the registration portal provides a simple and structured process for joining the MCD Mini League.

All registrations are managed through a centralized digital platform to ensure transparency, efficiency, and accessibility.

# ATHLETE REGISTRATION

## Register as an Athlete

Athlete registration provides access to:

- Club Participation

- League Competitions

- Athlete Profiles

- Development Programmes

- Talent Identification Opportunities

### Eligibility Requirements

Applicants must:

- Meet age-category requirements.

- Provide accurate information.

- Submit required documentation.

- Comply with league regulations.

### Required Documents

- Photograph

- Age Verification Document

- Identity Proof (where applicable)

- Parent/Guardian Consent

### Registration Process

Step 1 – Create Profile

Step 2 – Submit Information

Step 3 – Upload Documents

Step 4 – Verification

Step 5 – Registration Approval

# CLUB REGISTRATION

## Register a Community Sports Club

Organizations seeking affiliation may apply through the online registration portal.

### Registration Includes

- Club Information

- Governance Structure

- Office Bearer Details

- Facility Information

- Document Submission

### Benefits

- League Participation

- Club Recognition

- Athlete Development Support

- Resource Access

# CONTACT US

## Get in Touch

We are committed to supporting athletes, clubs, coaches, volunteers, parents, partners, and community members.

For inquiries, assistance, or support, please contact the relevant department.

## GENERAL INQUIRIES

For information regarding the MCD Mini League, programmes, and participation opportunities.

## REGISTRATION SUPPORT

For assistance with:

- Athlete Registration

- Club Registration

- Coach Registration

- Volunteer Registration

## TECHNICAL SUPPORT

For assistance related to:

- Website Access

- Login Issues

- Profile Management

- Digital Platform Support

## PARTNERSHIP INQUIRIES

For sponsorship, partnership, CSR, and collaboration opportunities.

## MEDIA INQUIRIES

For interviews, press requests, media coverage, and official communications.

## CONTACT FORM

Fields:

- Full Name

- Organization

- Email Address

- Phone Number

- Inquiry Type

- Subject

- Message

# FOOTER CONTENT

## QUICK LINKS

- Home

- About

- Clubs

- Tournament

- Teams

- Athletes

- Fixtures

- Results

- Standings

- Venues

- Media Centre

- Sponsors & Partners

- Contact

## RESOURCES

- Downloads

- FAQ

- Registration Guidelines

- Rules & Regulations

- Policies

## REGISTRATION

- Athlete Registration

- Club Registration

- Coach Registration

- Volunteer Registration

## CONNECT WITH US

Follow us on:

- Facebook

- Instagram

- X

- LinkedIn

- YouTube

## NEWSLETTER

Stay informed about competitions, community programmes, athlete achievements, and upcoming opportunities.

Field:

Email Address

Button:

Subscribe

# PRIVACY POLICY

## Privacy Commitment

The MCD Mini League is committed to protecting the privacy and personal information of all users, participants, athletes, coaches, volunteers, and stakeholders.

Information collected through the website will only be used for legitimate operational, communication, and programme management purposes.

## Information Collected

- Personal Information

- Contact Details

- Registration Information

- Participation Records

- Website Usage Information

## Data Protection

Appropriate measures will be implemented to protect user information from unauthorized access, misuse, or disclosure.

# TERMS & CONDITIONS

## Acceptance

By using the MCD Mini League website and related services, users agree to comply with all applicable policies, guidelines, and regulations.

## Website Usage

Users must:

- Provide accurate information.

- Use the platform responsibly.

- Respect intellectual property rights.

- Follow applicable regulations.

## Intellectual Property

All website content, branding, logos, graphics, documents, and digital assets remain the property of the MCD Mini League and its respective owners.

# CODE OF CONDUCT

## Our Commitment

The MCD Mini League is committed to creating safe, inclusive, respectful, and positive sporting environments.

All participants are expected to uphold these values.

## Expected Behaviour

Participants must:

- Demonstrate respect.

- Promote fair play.

- Encourage inclusion.

- Support athlete welfare.

- Act responsibly.

## Prohibited Behaviour

- Harassment

- Bullying

- Discrimination

- Abuse

- Unsportsmanlike Conduct

- Fraudulent Activities

Violations may result in disciplinary action.

# SAFEGUARDING POLICY

## Athlete Welfare First

The safety and well-being of athletes is the highest priority of the MCD Mini League.

The league is committed to providing environments where children and young people can participate safely, confidently, and positively.

## Safeguarding Principles

### Safety

Protect participants from harm and abuse.

### Respect

Treat all individuals with dignity and fairness.

### Inclusion

Ensure equal participation opportunities.

### Accountability

Maintain clear responsibilities and reporting mechanisms.

## Reporting Concerns

Any safeguarding concern, welfare issue, or inappropriate conduct should be reported immediately through the designated reporting channels.

All reports will be handled confidentially and in accordance with established procedures.

# Website Design

# MCD MINI LEAGUE

# WEBSITE DESIGN DOCUMENT

## UI/UX, Visual Design & Functional Specifications

Version 1.0

# 1. DESIGN OBJECTIVE

The MCD Mini League website should establish itself as Delhi's premier grassroots sports ecosystem platform.

The platform must:

- Promote sports participation.

- Drive club formation and registration.

- Support athlete development.

- Facilitate competition management.

- Enable community engagement.

- Showcase impact and achievements.

- Attract sponsors and partners.

- Build trust and credibility.

The design should feel modern, energetic, inclusive, and community-driven while maintaining the credibility of a government-supported initiative.

# 2. DESIGN PRINCIPLES

## Community First

Every page should reinforce the role of communities and clubs.

## Athlete-Centric

Athletes should be the visual focus of the platform.

## Mobile First

Most users will access the website through mobile devices.

## Action Oriented

Every page should encourage users to take action:

- Join a Club

- Start a Club

- Register

- View Fixtures

- Become a Partner

## Simple Navigation

Information should be accessible within 2–3 clicks.

# 3. WEBSITE STRUCTURE

HOME

ABOUT

├─ About League

├─ Vision & Mission

├─ Impact

├─ Governance

CLUBS

├─ About Clubs

├─ Club Directory

├─ Club Profile

├─ Start a Club

├─ Registration Guidelines

├─ Rules & Regulations

├─ Downloads

├─ FAQ

TOURNAMENT

├─ Overview

├─ Competition Format

├─ Rules & Regulations

├─ Fixtures

├─ Results

├─ Standings

TEAMS

├─ Team Directory

├─ Team Profile

ATHLETES

├─ Athlete Directory

├─ Athlete Profile

VENUES

MEDIA

├─ News

├─ Gallery

├─ Videos

SPONSORS & PARTNERS

REGISTER

├─ Athlete Registration

├─ Club Registration

CONTACT

# 4. VISUAL IDENTITY

## Brand Personality

Energetic

Youthful

Professional

Community-Focused

Inclusive

Inspirational

Trustworthy

## Visual Style

Large sports photography

Full-width banners

Bold typography

Modern cards

Rounded UI elements

Interactive content

Minimal clutter

Dynamic layouts

# 5. COLOR SYSTEM

## Primary Color

MCD Blue

HEX: #003B7A

Usage:

- Header

- Buttons

- Links

- Primary branding

## Secondary Color

Sports Orange

HEX: #F58220

Usage:

- CTA Buttons

- Highlights

- Hover States

## Success Color

HEX: #28A745

Usage:

- Completed registrations

- Positive indicators

## Alert Color

HEX: #DC3545

Usage:

- Errors

- Alerts

## Neutral Colors

Light Background

#F8F9FA

Dark Text

#212529

Border Grey

#E5E7EB

# 6. TYPOGRAPHY

## Heading Font

Montserrat Extra Bold

## Body Font

Poppins Regular

## Button Font

Montserrat Semi Bold

## Font Sizes

H1

56px

H2

42px

H3

32px

Body

18px

Mobile Body

16px

# 7. HEADER DESIGN

## Desktop

Left

League Logo

MCD Logo

SITDS Logo

Center

Navigation Menu

Right

Search

Register Button

Sticky Navigation

Enabled

## Mobile

Logo

Hamburger Menu

Register CTA

Sticky Header

# 8. HOME PAGE DESIGN

## Section 1: Hero Banner

Height:

100vh

Content Layout

Left Side

Headline

Subheadline

Description

CTA Buttons

Right Side

Sports Action Image

or

Video Banner

CTA Buttons

Register Now

Explore Clubs

View Fixtures

## Section 2: Impact Statistics

Layout

8 Animated Counter Cards

Cards

Total Clubs

Athletes

Coaches

Volunteers

Teams

Venues

Matches

Zones Covered

## Section 3: About the Movement

Split Layout

Image + Content

## Section 4: Community Clubs Network

Club Search Bar

Featured Clubs Carousel

Interactive Map

## Section 5: Athlete Journey

Horizontal Process Flow

Community

↓

Club

↓

Training

↓

Competition

↓

League

↓

Talent Pathway

## Section 6: Upcoming Fixtures

Fixture Cards

Date

Time

Venue

Category

## Section 7: Featured Athletes

Athlete Cards

Image

Name

Club

Statistics

## Section 8: News

Latest News Grid

3 Featured Stories

## Section 9: Sponsors

Partner Logo Carousel

# 9. ABOUT PAGE DESIGN

Hero Banner

Mission

Vision

Objectives

Impact

Governance

Leadership

Partners

Timeline

Components

Statistics

Infographics

Milestone Cards

# 10. CLUBS SECTION DESIGN

This is the most important section after Home.

## About Clubs

Hero Banner

Benefits Section

Impact Statistics

Development Pathway

Success Stories

## Club Directory

Search Bar

Filter Panel

Zone

Ward

Sport

Age Group

Display

Grid Layout

Map View

## Club Cards

Club Logo

Club Name

Location

Sports

Members

View Profile Button

## Club Profile

Cover Image

Logo

Club Details

Tabs

Overview

Sports

Coaches

Gallery

Facilities

Contact

# 11. START A CLUB PAGE

## Hero Section

Become a Community Sports Leader

## Eligibility Section

Icon Cards

## Benefits Section

Card Layout

## Required Structure

Organization Chart

President

Secretary

Proctor

Treasurer

Coordinator

## Required Documents

Checklist Layout

## Registration Journey

Interactive Timeline

Step 1

Review Guidelines

↓

Step 2

Prepare Documents

↓

Step 3

Apply

↓

Step 4

Verification

↓

Step 5

Approval

↓

Step 6

Activation

CTA

Start Registration

# 12. REGISTRATION GUIDELINES PAGE

Design Type

Knowledge Centre

Left Sidebar

Navigation

Right Content

Accordion Sections

Downloads

PDF Cards

Search Function

Enabled

# 13. RULES & REGULATIONS PAGE

Document Portal Design

Components

Search Bar

Category Filters

PDF Downloads

Print Button

# 14. DOWNLOADS PAGE

Resource Library Design

Resource Cards

Document Icon

Title

Description

Download Button

Filter Categories

Club Resources

Forms

Policies

Templates

Handbooks

# 15. FAQ PAGE

Searchable FAQ

Accordion Layout

Categories

Club Formation

Registration

Competitions

Athletes

Coaches

Volunteers

# 16. TOURNAMENT DESIGN

Hero Banner

Overview

Competition Structure

League Pyramid

Visual Structure

Diamond League

↓

Gold League

↓

Silver League

↓

Bronze League

Competition Calendar

Timeline View

# 17. FIXTURES PAGE

Filter Panel

Calendar

List View

Fixture Card

Teams

Date

Venue

Category

Status

# 18. RESULTS PAGE

Result Cards

Score

Match Report

Athlete of Match

# 19. STANDINGS PAGE

Professional League Table

Columns

Position

Team

Played

Won

Drawn

Lost

GD

Points

Mobile

Swipe Table

# 20. TEAMS DESIGN

## Team Directory

Grid Layout

Team Cards

## Team Profile

Cover Banner

Statistics

Squad

Fixtures

Results

Gallery

# 21. ATHLETES DESIGN

## Athlete Directory

Search

Filters

Grid View

## Athlete Profile

Hero Image

Statistics

Achievements

Gallery

Performance History

# 22. VENUES DESIGN

Venue Directory

Map Integration

Venue Profile

Photos

Facilities

Directions

Contact

# 23. MEDIA CENTRE

## News

Magazine Layout

## Gallery

Masonry Grid

## Videos

Video Library

# 24. SPONSORS & PARTNERS

Hero Banner

Partnership Benefits

Sponsor Categories

Current Partners

Sponsor Logos

CTA

Become a Partner

Download Sponsorship Deck

# 25. REGISTRATION PORTAL

Unified Registration Hub

Cards

Athlete Registration

Club Registration

Coach Registration

Volunteer Registration

# 26. FORM DESIGN

Multi-Step Forms

Progress Bar

Step Indicator

Save & Continue

Document Upload

Review & Submit

Success Screen

# 27. CONTACT PAGE

Hero Banner

Contact Cards

Contact Form

Map

Support Information

# 28. FOOTER DESIGN

Column 1

About

Column 2

Clubs

Column 3

Tournament

Column 4

Resources

Column 5

Contact

Bottom Strip

Copyright

Privacy Policy

Terms

Social Media

Newsletter Signup

# 29. RESPONSIVE DESIGN

Desktop

1920px

Laptop

1440px

Tablet

768px

Mobile

375px

Requirements

Fast Loading

Responsive Tables

Touch-Friendly Buttons

Sticky CTAs

Optimized Forms

# 30. KEY UI COMPONENTS

Primary Button

Secondary Button

Statistic Card

Club Card

Athlete Card

Team Card

Venue Card

News Card

Sponsor Card

Download Card

FAQ Accordion

Timeline Component

League Table

Search Bar

Filter Panel

Registration Form

# Sponsorship Agreement

MCD MINI LEAGUE

SPONSORSHIP FRAMEWORK

Commercial Rights, Agreement Template, Inventory, Deliverables & Operations Manual

Supported by the Municipal Corporation of Delhi (MCD)

Managed by the Sports Infrastructure & Talent Development Society (SITDS)

Play. Compete. Grow.

# SPONSORSHIP OPPORTUNITIES — AT A GLANCE

| Category | Investment | Slots | Positioning |
| --- | --- | --- | --- |
| Title Sponsor | ₹1 Crore | 1 | Exclusive title association; "MCD Mini League, presented by [Brand]"; maximum city-wide visibility |
| Co-Sponsor | ₹50 Lakh | 2 | Strong branding across league, club, digital, and community touchpoints |
| Official Partner | ₹15 Lakh | 4 | Official association with agreed branding and activation access |
| Category Sponsor | ₹5 Lakh | 5 | Exclusive within a category: Banking, Education, Healthcare, Sports Equipment, Nutrition, Technology, Mobility, Hospitality, Insurance, Media |
| In-Kind Sponsor | Products / Services | Multiple | Equipment, Hydration, Nutrition/Dairy, Medical, Apparel, Technology, Transport, Media & Production |

The MCD Mini League is a city-wide grassroots sports ecosystem supported by the Municipal Corporation of Delhi and managed by SITDS, spanning Community Clubs, Under-9 and Under-11 Boys' and Girls' competition, and a Bronze–Silver–Gold–Diamond league pyramid with promotion and relegation. This framework reflects the long-term value of that ecosystem, not merely event-day branding.

# PART A — STANDARD SPONSORSHIP AGREEMENT

This Sponsorship Agreement Template ("Agreement") is designed for use across all sponsorship categories of the MCD Mini League — Title Sponsor, Co-Sponsor, Official Partner, Category Sponsor, and In-Kind Sponsor. Bracketed fields [ ] are to be completed for each specific sponsor and category prior to execution.

## 1. Agreement Overview

This Agreement sets out the terms on which [SPONSOR NAME] ("Sponsor") shall sponsor and be associated with the MCD Mini League ("League") for the season/period commencing [START DATE] and ending [END DATE] ("Term"), in the sponsorship category of [Title Sponsor / Co-Sponsor / Official Partner / Category Sponsor — specify category / In-Kind Sponsor].

## 2. Definitions

"League": the MCD Mini League, a grassroots community sports ecosystem operating under the support of the Municipal Corporation of Delhi (MCD) and managed by the Sports Infrastructure & Talent Development Society (SITDS), comprising the Community Club Network, Under-9 and Under-11 age categories, Boys' and Girls' competitions, and the Bronze, Silver, Gold and Diamond League tiers.

"Organizer": SITDS acting as the operating body of the League, together with MCD in its capacity as institutional supporter.

"Sponsor": the entity named in this Agreement that has committed sponsorship consideration in exchange for the rights set out herein.

"Sponsorship Fee": the cash and/or in-kind consideration payable by the Sponsor as set out in Schedule 1.

"Marks": the trademarks, logos, brand names, and other identifying marks of the League, the Sponsor, MCD, and SITDS respectively.

"Territory": the National Capital Territory of Delhi, or such wider territory as agreed in Schedule 1.

"Season": each annual cycle of League competition, festivals, and development programming.

"League Assets": all branding, digital, media, competition, club, athlete, venue, and community assets described in Part B (Sponsorship Inventory) of the framework document of which this Agreement forms part.

## 3. Parties

This Agreement is entered into between:

•     The Sports Infrastructure & Talent Development Society (SITDS), as Organizer of the MCD Mini League, with the institutional support of the Municipal Corporation of Delhi (MCD); and

•     [SPONSOR LEGAL NAME], having its registered office at [ADDRESS] ("Sponsor").

(each a "Party" and together the "Parties")

## 4. Sponsorship Rights

Subject to full and timely payment of the Sponsorship Fee and compliance with this Agreement, the Organizer grants the Sponsor the rights set out in this Section 4 and in Schedule 1 (Category-Specific Rights), commensurate with the Sponsor's category (Title Sponsor / Co-Sponsor / Official Partner / Category Sponsor / In-Kind Sponsor) as detailed in Part E (Commercial Rights & Benefits Framework).

### 4.1 Naming Rights

Where applicable to the Sponsor's category (Title Sponsor only, unless otherwise agreed), the right to have the League referred to as "MCD Mini League, presented by [Sponsor]" or such other naming convention as agreed in writing, across all official League communications, venues, and collateral for the Term.

### 4.2 Branding Rights

The right to place the Sponsor's Marks on the League Assets designated to the Sponsor's category, including as applicable: venue and ground branding, entrance arch branding, event backdrops, trophy and medal branding, team areas, registration areas, and match day signage, in accordance with the Branding Guidelines (Section 14).

### 4.3 Marketing Rights

The right to reference its association with the League in the Sponsor's own marketing, advertising, and promotional materials, subject to prior written approval of the Organizer for any use of League or MCD/SITDS Marks, and subject to the exclusivity provisions in Section 15.

### 4.4 Digital Rights

The right to branding placement and mentions across the League's digital assets designated to the Sponsor's category, which may include the website homepage, sponsor landing pages, registration pages, social media posts and campaigns, email marketing, newsletters, and digital advertising inventory, as set out in Part C (Sponsor Deliverables Matrix).

### 4.5 Activation Rights

The right to conduct on-ground and digital brand activations at agreed League touchpoints, including sponsor experience zones, sampling, contests, and community engagement activities, subject to activation plans being submitted to and approved by the Organizer at least [14] days in advance.

### 4.6 Hospitality Rights

Where applicable to the Sponsor's category, the right to hospitality benefits including VIP passes, reserved seating at finals, sponsor lounge access, and invitations to award ceremonies and season milestone events, in the quantities set out in Schedule 1.

### 4.7 Intellectual Property Rights

All Marks remain the exclusive property of their respective owners. No Party grants the other any ownership interest in its Marks. Each Party grants the other a limited, non-exclusive, non-transferable, royalty-free licence to use its Marks solely for the purposes of this Agreement and only during the Term. All goodwill arising from use of a Party's Marks accrues solely to that Party. Neither Party may register, or assist a third party in registering, any Mark confusingly similar to the other Party's Marks.

## 5. Organizer Obligations

•     Deliver the League Assets and deliverables assigned to the Sponsor's category as set out in Part C (Sponsor Deliverables Matrix) and Schedule 1.

•     Provide the Sponsor with a single point of contact for sponsorship servicing, in accordance with Part F (Sponsor Operations Manual).

•     Use reasonable efforts to ensure League fixtures, festivals, and ceremonies proceed as scheduled, subject to Force Majeure.

•     Provide the Sponsor with periodic reporting on deliverable fulfilment, reach, and impact as set out in Part C and Part D.

•     Maintain the reputation, safety standards, and child-protection standards appropriate to a youth sports ecosystem, and ensure Sponsor activations are conducted consistently with these standards.

•     Not grant rights to any other sponsor that are inconsistent with the exclusivity granted to the Sponsor under Section 15.

## 6. Sponsor Obligations

•     Pay the Sponsorship Fee (cash and/or in-kind, as applicable) in accordance with the Payment Terms in Section 13.

•     Supply all branding materials, logos, and creative assets required for activation within the timelines specified by the Organizer.

•     Ensure all Sponsor-provided products, services, or in-kind contributions meet applicable safety and quality standards, particularly given the League's youth participant base.

•     Comply with the Branding Guidelines (Section 14) and obtain prior written approval before any public communication referencing the League, MCD, or SITDS.

•     Not engage in any conduct that could bring the League, MCD, or SITDS into disrepute.

•     Ensure any personnel deployed at League venues comply with the Organizer's child-safeguarding and code-of-conduct policies.

## 7. Payment Terms

The Sponsorship Fee for the Sponsor's category is set out in Schedule 1. Unless otherwise agreed in writing:

•     50% of the cash Sponsorship Fee is payable within [15] days of execution of this Agreement, and the remaining 50% within [15] days of the League's mid-season milestone.

•     In-kind contributions shall be delivered in accordance with the delivery schedule agreed in Schedule 1 and shall be valued at fair market price for the purposes of this Agreement.

•     All amounts are exclusive of applicable taxes (including GST), which shall be payable in addition at the prevailing rate.

•     Late payment beyond [15] days of the due date entitles the Organizer to suspend the Sponsor's rights under this Agreement until payment is received, without prejudice to other remedies.

## 8. Branding Guidelines

•     All use of League, MCD, and SITDS Marks must follow the official brand guidelines issued by the Organizer, including approved logo lock-ups, colour palettes, and minimum clear-space requirements.

•     No alteration, distortion, or unauthorised combination of Marks with third-party marks is permitted.

•     All creative execution involving youth participants must comply with child-safeguarding and image-consent protocols.

•     The Organizer reserves the right to reject any branding execution that does not meet quality or safeguarding standards, acting reasonably and providing reasons in writing.

## 9. Exclusivity

Category exclusivity applies as follows: the Title Sponsor and Category Sponsors (within their designated product/service category, e.g. Banking, Education, Healthcare, Sports Equipment, Nutrition, Technology, Mobility, Hospitality, Insurance, Media) receive exclusivity against direct competitors within the same category for the Term, as specified in Schedule 1. Co-Sponsors and Official Partners receive no automatic category exclusivity unless expressly agreed in Schedule 1. In-Kind Sponsors receive exclusivity only within their specific product/service line (e.g. hydration, apparel, equipment).

## 10. Confidentiality

Each Party shall keep confidential all non-public commercial, financial, and operational information disclosed by the other Party in connection with this Agreement, and shall not disclose such information to any third party without prior written consent, except as required by law or to professional advisors bound by equivalent confidentiality obligations. This obligation survives termination of this Agreement for a period of [2] years.

## 11. Indemnity

Each Party ("Indemnifying Party") shall indemnify and hold harmless the other Party, its officers, employees, and agents from and against any claims, losses, damages, and reasonable costs arising from: (a) the Indemnifying Party's breach of this Agreement; (b) the Indemnifying Party's negligence or wilful misconduct; or (c) any claim that the Indemnifying Party's Marks or materials infringe the intellectual property rights of a third party. This indemnity does not extend to indirect or consequential losses.

## 12. Force Majeure

Neither Party shall be liable for any failure or delay in performance under this Agreement to the extent caused by circumstances beyond its reasonable control, including natural disasters, government action, civil unrest, pandemic, or extreme weather. The affected Party shall notify the other promptly and both Parties shall use reasonable efforts to mitigate impact, including rescheduling affected deliverables. If Force Majeure continues beyond [60] days, either Party may terminate this Agreement on written notice, with fees adjusted on a pro-rata basis for deliverables actually fulfilled.

## 13. Termination

•     Either Party may terminate this Agreement for material, uncured breach by the other Party following [30] days' written notice specifying the breach, if such breach remains uncured at the end of that period.

•     The Organizer may terminate immediately on written notice if the Sponsor's conduct or products bring, or are reasonably likely to bring, the League, MCD, or SITDS into disrepute, or breach child-safeguarding standards.

•     Upon termination, all outstanding fees for deliverables already fulfilled become immediately payable, and all licences to use Marks granted under this Agreement immediately cease, save for wind-down of previously produced materials for a period of [30] days.

## 14. Dispute Resolution

The Parties shall first attempt to resolve any dispute arising from this Agreement through good-faith negotiation between senior representatives within [30] days. If unresolved, the dispute shall be referred to mediation, and failing settlement, to arbitration under the Arbitration and Conciliation Act, 1996, with the seat of arbitration in Delhi and proceedings conducted in English.

## 15. Governing Law

This Agreement is governed by and construed in accordance with the laws of India, and the courts at Delhi shall have exclusive jurisdiction, subject to the arbitration provisions in Section 14.

## 16. General Provisions

•     Entire Agreement: This Agreement, including its Schedules, constitutes the entire agreement between the Parties and supersedes all prior discussions.

•     Amendment: No amendment is effective unless in writing and signed by authorised representatives of both Parties.

•     Assignment: Neither Party may assign this Agreement without the prior written consent of the other, not to be unreasonably withheld.

•     Notices: All notices shall be in writing and delivered to the addresses specified in Schedule 2.

•     Severability: If any provision is held invalid, the remainder of this Agreement continues in full force.

## Schedule 1 — Category-Specific Rights & Fees

[To be completed per sponsor: Sponsorship Category / Sponsorship Fee / Payment Schedule / Exclusivity Category / Specific Deliverables Reference (Part C) / Term / Territory]

## Schedule 2 — Notice Addresses

Organizer: SITDS, [Address] — Attn: [Name/Title]. Sponsor: [Sponsor Legal Name], [Address] — Attn: [Name/Title].

## Signature Page

IN WITNESS WHEREOF, the Parties have executed this Agreement as of the date first written below.

For and on behalf of SITDS (Organizer)                    For and on behalf of [Sponsor]

Name: ______________________                          	Name: ______________________

Designation: ________________                             Designation: ________________

Signature: __________________                             Signature: __________________

Date: _______________________                         	Date: _______________________

# PART B — SPONSORSHIP INVENTORY

The MCD Mini League's sponsorship inventory spans the full ecosystem — league, club, athlete, competition, venue, digital, media, and community assets  reflecting its role as a season-long, city-wide development pathway rather than a single event.

### League Assets

•     League Naming Rights

•     Trophy Branding

•     Medal Branding

•     League Tier Branding (Diamond, Gold, Silver, Bronze)

•     Championship Branding

•     Finals Branding

### Club Assets

•     Club Development Programme

•     Club Registration Portal

•     Club Directory

•     Club Workshops

•     Club Resource Centre

### Athlete Assets

•     Athlete Registration

•     Athlete Profiles

•     Talent Development Programme

•     Athlete Awards

•     Player Recognition Programmes

### Competition Assets

•     Fixtures

•     Results

•     Standings

•     Match Centre

•     Match Day Branding

### Venue Assets

•     Entry Gates

•     Arch Gates

•     Backdrops

•     Ground Branding

•     Team Areas

•     Registration Areas

•     Event Signage

### Digital Assets

•     Website Homepage

•     Sponsor Landing Pages

•     Registration Pages

•     Social Media Posts

•     Social Media Campaigns

•     Email Marketing

•     Newsletters

•     Digital Advertising

### Media Assets

•     Press Releases

•     Media Interviews

•     Sponsor Mentions

•     Highlight Videos

•     Promotional Content

### Community Assets

•     School Outreach Programmes

•     Community Events

•     Volunteer Programmes

•     Coaching Clinics

•     Club Engagement Activities

# PART C — SPONSOR DELIVERABLES MATRIX

The matrix below sets out 76 deliverables across nine functional categories, mapped against the five sponsorship categories. ✓ = Included · △ = Limited / Category-Specific · ✗ = Not Included. Category Sponsor entries reflect visibility specific to the sponsor's declared category (e.g. Banking, Nutrition, Technology); In-Kind entries reflect on-ground visibility tied to the sponsor's product/service contribution.

| # | Category | Deliverable | Title | Co-Sponsor | Official Partner | Category Sponsor | In-Kind |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Branding | League Naming Rights (Presenting Sponsor Credit) | ✓ | ✓ | ✓ | △ | △ |
| 2 | Branding | Trophy Branding | ✓ | ✓ | ✓ | △ | △ |
| 3 | Branding | Medal Branding | ✓ | ✓ | △ | △ | ✗ |
| 4 | Branding | League Tier Branding (Diamond / Gold / Silver / Bronze) | ✓ | ✓ | △ | △ | ✗ |
| 5 | Branding | Championship & Finals Branding | ✓ | ✓ | ✓ | △ | △ |
| 6 | Branding | Venue & Ground Branding | ✓ | ✓ | △ | △ | ✓ |
| 7 | Branding | Entrance Arch Gate Branding | ✓ | ✓ | △ | △ | ✓ |
| 8 | Branding | Event Backdrop Branding | ✓ | ✓ | △ | △ | ✓ |
| 9 | Branding | Team Area & Registration Area Branding | ✓ | △ | △ | △ | ✓ |
| 10 | Branding | Match Day Signage & Buntings | ✓ | △ | △ | △ | ✓ |
| 11 | Digital | Website Homepage Logo Placement | ✓ | ✓ | ✓ | △ | △ |
| 12 | Digital | Dedicated Sponsor Landing Page | ✓ | ✓ | △ | △ | ✗ |
| 13 | Digital | Registration Page Branding | ✓ | △ | △ | △ | ✓ |
| 14 | Digital | Social Media Posts (Tagged Mentions) | ✓ | ✓ | △ | △ | ✓ |
| 15 | Digital | Social Media Campaign Features | ✓ | ✓ | △ | △ | ✗ |
| 16 | Digital | Email Marketing Inclusion | ✓ | △ | △ | ✗ | ✗ |
| 17 | Digital | Newsletter Placement | ✓ | △ | △ | ✗ | ✗ |
| 18 | Digital | Digital Advertising Inventory (Banners) | ✓ | ✓ | △ | △ | ✗ |
| 19 | Digital | Mobile Registration Portal Branding | ✓ | △ | △ | ✗ | ✗ |
| 20 | Digital | Sponsor Recognition on Digital Match Centre | ✓ | ✓ | △ | △ | ✗ |
| 21 | Media | Press Release Mentions | ✓ | ✓ | △ | △ | ✗ |
| 22 | Media | Media Interview Opportunities | ✓ | ✓ | △ | △ | ✗ |
| 23 | Media | Sponsor Mentions in Match/Event Commentary | ✓ | ✓ | △ | △ | ✓ |
| 24 | Media | Highlight Video Branding (Bumper/Logo) | ✓ | ✓ | △ | △ | ✗ |
| 25 | Media | Promotional Content Features | ✓ | △ | △ | ✗ | ✗ |
| 26 | Media | Match Day Live Coverage Branding | ✓ | ✓ | △ | △ | ✗ |
| 27 | Media | Photography & Content Credits | ✓ | △ | △ | △ | ✓ |
| 28 | Media | Co-Branded Season Recap Film | ✓ | △ | △ | ✗ | ✗ |
| 29 | Community | School Outreach Programme Branding | ✓ | ✓ | △ | △ | ✓ |
| 30 | Community | Community Sports Festival Branding | ✓ | ✓ | △ | △ | ✓ |
| 31 | Community | Volunteer Programme Association | ✓ | △ | △ | △ | ✓ |
| 32 | Community | Coaching Clinic Branding | ✓ | △ | △ | △ | ✓ |
| 33 | Community | Club Engagement Activity Branding | ✓ | △ | △ | △ | ✓ |
| 34 | Community | Grassroots Festival On-Ground Presence | ✓ | ✓ | △ | △ | ✓ |
| 35 | Community | Community Sports Day Naming Rights | ✓ | ✓ | △ | △ | ✗ |
| 36 | Community | Local Outreach Collateral Branding | ✓ | △ | △ | △ | ✓ |
| 37 | Club Development | Club Registration Portal Branding | ✓ | ✓ | △ | △ | ✗ |
| 38 | Club Development | Club Directory Listing | ✓ | △ | △ | ✗ | ✗ |
| 39 | Club Development | Club Workshop Sponsorship | ✓ | △ | △ | △ | ✓ |
| 40 | Club Development | Club Resource Centre Branding | ✓ | △ | △ | ✗ | ✗ |
| 41 | Club Development | Club Development Programme Naming | ✓ | ✓ | △ | △ | ✗ |
| 42 | Club Development | Club Onboarding Kit Branding | ✓ | △ | △ | △ | ✓ |
| 43 | Club Development | Club Certification Co-Branding | ✓ | △ | △ | ✗ | ✗ |
| 44 | Club Development | Club Newsletter Feature | ✓ | △ | △ | ✗ | ✗ |
| 45 | Athlete Development | Athlete Registration Branding | ✓ | △ | △ | ✗ | ✗ |
| 46 | Athlete Development | Athlete Profile Page Sponsorship | ✓ | △ | △ | ✗ | ✗ |
| 47 | Athlete Development | Talent Development Programme Naming | ✓ | ✓ | △ | △ | ✗ |
| 48 | Athlete Development | Athlete Awards Sponsorship | ✓ | ✓ | △ | △ | ✗ |
| 49 | Athlete Development | Player Recognition Programme | ✓ | ✓ | △ | △ | ✗ |
| 50 | Athlete Development | Athlete Certificate Branding | ✓ | △ | △ | △ | ✓ |
| 51 | Athlete Development | Scouting Programme Association | ✓ | ✓ | △ | △ | ✗ |
| 52 | Athlete Development | Performance Tracking Tool Branding | ✓ | △ | △ | ✗ | ✗ |
| 53 | Competition | Fixtures Page Branding | ✓ | △ | △ | ✗ | ✗ |
| 54 | Competition | Results Page Branding | ✓ | △ | △ | ✗ | ✗ |
| 55 | Competition | Standings Page Sponsorship | ✓ | △ | △ | ✗ | ✗ |
| 56 | Competition | Match Centre Sponsorship | ✓ | ✓ | △ | △ | ✗ |
| 57 | Competition | Match Day Branding | ✓ | ✓ | △ | △ | ✓ |
| 58 | Competition | League Tier Title Association | ✓ | ✓ | ✓ | △ | △ |
| 59 | Competition | Promotion & Relegation Ceremony Branding | ✓ | ✓ | △ | △ | ✗ |
| 60 | Competition | Season Opening/Closing Ceremony Branding | ✓ | ✓ | ✓ | △ | △ |
| 61 | Hospitality | VIP Hospitality Passes | ✓ | ✓ | △ | △ | ✗ |
| 62 | Hospitality | Sponsor Experience Zone | ✓ | ✓ | △ | △ | ✓ |
| 63 | Hospitality | Reserved Seating at Finals | ✓ | ✓ | △ | △ | ✗ |
| 64 | Hospitality | Meet & Greet Access with Athletes | ✓ | △ | △ | ✗ | ✗ |
| 65 | Hospitality | Sponsor Lounge Access | ✓ | ✓ | △ | △ | ✗ |
| 66 | Hospitality | Award Ceremony Stage Presence | ✓ | ✓ | ✓ | △ | △ |
| 67 | Hospitality | Guest Invitations to Finals | ✓ | △ | △ | ✗ | ✗ |
| 68 | Hospitality | Sponsor Recognition Wall / Plaque | ✓ | △ | △ | △ | ✓ |
| 69 | Reporting | Post-Season Impact Report | ✓ | ✓ | △ | △ | ✗ |
| 70 | Reporting | Quarterly Performance Report | ✓ | △ | △ | ✗ | ✗ |
| 71 | Reporting | Reach & Impressions Report | ✓ | ✓ | △ | △ | ✗ |
| 72 | Reporting | Community Impact Data Summary | ✓ | △ | △ | △ | ✓ |
| 73 | Reporting | Digital Analytics Report | ✓ | △ | △ | ✗ | ✗ |
| 74 | Reporting | Custom ROI Report | ✓ | ✓ | △ | △ | ✗ |
| 75 | Reporting | Annual Partnership Review Meeting | ✓ | ✓ | △ | △ | ✗ |
| 76 | Reporting | Asset Utilisation & Compliance Report | ✓ | △ | △ | ✗ | ✗ |

# PART E — COMMERCIAL RIGHTS & BENEFITS FRAMEWORK

This framework defines the rights and benefits attached to each sponsorship category, consistent with the Sponsor Deliverables Matrix in Part C.

## Title Sponsor (₹1 Crore · 1 Slot)

Rights Granted: Presenting/naming rights ("MCD Mini League, presented by [Sponsor]"), first right of renewal, category exclusivity, speaking opportunities at League events.

Branding Visibility: Maximum — venue, trophy, medal, arch gates, backdrops, team areas, all League tiers.

Community Reach: Full access across all participating schools, community clubs, and city-wide festivals.

Digital Reach: Homepage logo, sponsor landing page, full social and email inclusion.

Activation Opportunities: Dedicated sponsor experience zones at all major fixtures and finals.

Hospitality Benefits: VIP passes, reserved seating, award-ceremony stage presence, guest invitations to finals.

Data & Reporting Benefits: Full post-season impact report, quarterly reporting, custom ROI report.

Recognition Opportunities: Premier billing across all League communications and ceremonies.

## Co-Sponsor (₹50 Lakh · 2 Slots)

Rights Granted: Strategic association across league, club, digital, and community assets; partner association with youth development positioning.

Branding Visibility: Strong — logo presence across key league touchpoints and event-day branding.

Community Reach: Broad reach across community clubs and festivals.

Digital Reach: Digital communication visibility, social media mentions.

Activation Opportunities: Participation in on-ground activation at major fixtures.

Hospitality Benefits: VIP passes and access to key ceremonies.

Data & Reporting Benefits: Quarterly performance report and reach summary.

Recognition Opportunities: Strategic partner billing on League collateral.

## Official Partner (₹15 Lakh · 4 Slots)

Rights Granted: Official association with the League and access to agreed branding and activation opportunities on select assets.

Branding Visibility: Presence on select league assets, venues, and collateral.

Community Reach: Community engagement opportunities within agreed scope.

Digital Reach: Digital promotions and visibility across specific categories.

Activation Opportunities: Activation at designated touchpoints, subject to Organizer approval.

Hospitality Benefits: Limited passes to select events.

Data & Reporting Benefits: Reach summary and digital analytics extract.

Recognition Opportunities: "Official Partner" billing on relevant assets.

## Category Sponsor (₹5 Lakh · 5 Slots)

Rights Granted: Exclusive sponsorship within a specific category (Banking, Education, Healthcare, Sports Equipment, Nutrition, Technology, Mobility, Hospitality, Insurance, or Media Partner).

Branding Visibility: Category-specific visibility on designated assets only.

Community Reach: Targeted audience segments aligned to the sponsor's category.

Digital Reach: Product/service association on relevant digital touchpoints.

Activation Opportunities: Targeted activation opportunities within the sponsor's category.

Hospitality Benefits: Not included, unless separately negotiated.

Data & Reporting Benefits: Category-specific reach data on request.

Recognition Opportunities: Category Sponsor billing (e.g. "Official Nutrition Partner").

## In-Kind Sponsor (Products, Services & Experiences)

Rights Granted: High-visibility support in exchange for equipment, hydration, nutrition, apparel, medical, transport/logistics, technology, or media/production contributions, without direct cash sponsorship.

Branding Visibility: On-ground visibility tied to point of product/service delivery (e.g. hydration stations, medical tents, kit branding).

Community Reach: Direct touchpoint with athletes, clubs, and families at point of service.

Digital Reach: Limited — social media acknowledgement of contribution.

Activation Opportunities: Operational-point activation (e.g. sampling at hydration/nutrition stations).

Hospitality Benefits: Not included as standard.

Data & Reporting Benefits: Community impact acknowledgement in post-season report.

Recognition Opportunities: Named recognition as official [Equipment/Hydration/Nutrition/Apparel/Medical/Technology/Transport/Media] Partner.

# PART F — SPONSOR OPERATIONS MANUAL

This manual sets the standard operating procedures for servicing sponsors throughout the season, ensuring consistent, professional fulfilment across all sponsorship categories.

## 1. Sponsor Onboarding

•     Kick-off call within 5 working days of contract execution to align on category, deliverables, and key contacts.

•     Issue Sponsor Welcome Pack: brand guidelines, League calendar, deliverables matrix (Part C), and contact directory.

•     Collect Sponsor brand assets (logos, brand guidelines, product images, approved messaging) via a shared asset portal.

•     Assign a dedicated Sponsor Relationship Manager (SRM) as single point of contact for the Term.

## 2. Asset Collection Process

•     Standardised asset request form issued at onboarding, with a 10-working-day submission deadline.

•     Assets logged against the Deliverable Tracking Sheet (Part D) with a unique Deliverable ID.

•     Version control maintained for all creative files; only Organizer-approved final versions are used in production.

## 3. Branding Approval Workflow

•     Sponsor submits creative/branding execution to the SRM for review.

•     Organizer's brand team reviews within 3 working days against brand guidelines and child-safeguarding standards.

•     Approved / Changes Requested / Rejected status logged in the tracking sheet, with reasons provided for any rejection.

•     Final sign-off required from both Organizer and Sponsor before production or publication.

## 4. Activation Planning

•     Sponsors submit activation plans at least 14 days ahead of the relevant fixture, festival, or ceremony.

•     Operations team confirms venue logistics, space allocation, and safety compliance.

•     Joint walkthrough conducted for major activations (Title/Co-Sponsor tier) ahead of event day.

## 5. Deliverable Fulfilment

•     All deliverables tracked against the Deliverable Tracking Sheet (Part D), with owner, timeline, and status fields updated weekly.

•     Proof of delivery (photographs, screenshots, analytics exports, or signed confirmation) collected for every deliverable.

•     Escalation path for at-risk deliverables: SRM flags to Operations Lead at 70% of timeline elapsed if status is not "In Progress" or "Completed".

## 6. Reporting Standards

•     Quarterly Sponsor Performance Report covering deliverable completion rate, reach/impressions, and community engagement metrics.

•     Post-Season Impact Report covering full-season fulfilment, athlete/club participation numbers, and qualitative case studies.

•     Custom ROI reporting available to Title and Co-Sponsor tiers on request.

## 7. Sponsor Communication SOP

•     SRM to provide monthly status updates to each active sponsor, regardless of category.

•     All sponsor queries acknowledged within 24 hours and resolved or escalated within 5 working days.

•     Any material change to the League calendar or format communicated to sponsors within 48 hours.

## 8. Renewal & Retention Strategy

•     Renewal conversation initiated at 75% of Term completion, beginning with Title Sponsor (first right of renewal).

•     Season-end review meeting presenting the Post-Season Impact Report and proposed renewal terms.

•     Loyalty considerations for multi-season sponsors: priority category exclusivity and enhanced hospitality allocation.

•     Exit survey for non-renewing sponsors to capture feedback for continuous improvement.

# To be reviewed -Club Registration Process

MCD MINI LEAGUE (MML)

CLUB REGISTRATION - STANDARD OPERATING PROCEDURE

Registration, Verification, Approval and Onboarding of Clubs

Football & Cricket | Under-9 & Under-11 | Boys & Girls | Delhi-NCR

| Issuing Authority | Municipal Corporation of Delhi (MCD), Education Department, in partnership with Khelo Tech & Strategy Pvt. Ltd. |
| --- | --- |
| Document Reference | MCD/Edn/MML/SOP/2025-26/01 |
| Version | 1.0 |
| Effective Date | [DD/MM/2026] |
| Applicability | All MCD zones, non-MCD Government and Private zones, academies, community and corporate clubs participating in the MCD Mini League across Delhi-NCR |
| Classification | Official - For Circulation to All Stakeholders |

# TABLE OF CONTENTS

# 1. Introduction

## 1.1 Purpose

This Standard Operating Procedure (SOP) establishes the standardized, technology-enabled process governing the registration, verification, approval, and onboarding of Clubs participating in the MCD Mini Football League (MMFL). It is issued to ensure that every Club is registered through a uniform, transparent, auditable, and legally defensible process.

## 1.2 Objectives

•     To establish a single, government-endorsed pathway for Club formation and registration across Delhi-NCR.

•     To ensure standardization of eligibility, documentation, verification, and approval across all 12 MCD Zones.

•     To safeguard the core motive of the League - grassroots talent identification - through accurate, fraud-resistant registration and age-verification protocols.

•     To enable a digital-first, paperless registration workflow through the Game Management System (GMS).

•     To establish clear roles, timelines, and escalation paths so that no application remains unresolved beyond the prescribed period.

•     To protect the safety and welfare of minor participants through Child Protection and Safeguarding compliance embedded in the registration process.

## 1.3 Scope

This SOP applies to the end-to-end lifecycle of Club registration - from issuance of the Government Notice through to a Club attaining 'Ready for League' status and fixture eligibility. It initially covers Football, U-9 and U-11 age categories, Boys' and Girls' teams, and is applicable uniformly to MCD Clubs and Non-MCD Clubs.

## 1.4 Applicability

•     All  of Delhi and the 12 pre-formed MCD Clubs (one per Zone).

•     Academies, NGOs, community clubs, and corporate clubs seeking affiliation under the eligibility criteria in Section 3.

•     All League functionaries: Club Managers, External Club Supervisors, Zone Coordinators, Zone Operations Leads, the League Director, and the Technology Partner (Khelo Tech & Strategy Pvt. Ltd.).

## 1.5 Authority Issuing this SOP

This SOP is issued under the authority of the Commissioner, Municipal Corporation of Delhi, through the Education Department, in partnership with the League's Technology and Operations Partner, Khelo Tech & Strategy Pvt. Ltd., and endorsed for sport-specific implementation by the All India Football Federation (AIFF).

## 1.6 Definitions

| Term | Definition |
| --- | --- |
| Club | A registered zonal entity fielding U-9 and U-11 Boys' and Girls' teams in Football under the League. |
| Cluster | A joint Club formed by 2 or more zones pooling players to meet the minimum fielding requirement. |
| Club Manager | The individual nominated by a Club to manage day-to-day registration, roster, and league operations for that Club. |
| External Club Supervisor | A neutral, independent official - not a coach, parent, teacher, or principal of the Club - appointed to oversee compliance and conduct. |
| Zone | One of the 12 administrative divisions of MCD, each with a designated Zone Coordinator. |
| GMS | Game Management System - the centralized digital registration, verification, and match-management platform for the League. |
| Ready for League | The final registration status confirming a Club's players, documents, fees, and supervisor assignment are fully verified and approved. |

## 1.7 Abbreviations

| Abbreviation | Expansion |
| --- | --- |
| MMFL | MCD Mini Football League |
| MCD | Municipal Corporation of Delhi |
| DoE | Directorate of Education, Government of NCT of Delhi |
| AIFF | All India Football Federation |
| GMS | Game Management System |
| ZC | Zone Coordinator |
| ZOL | Zone Operations Lead |
| ECS | External Club Supervisor |

# 2. Governance Framework

## 2.1 League Hierarchy

The League operates on a four-tier governance structure: (i) the MCD Commissioner and Education Department as the constitutional and administrative authority; (ii) the League Director, appointed jointly by MCD and Khelo Tech, as the operational head of the League; (iii) Zone Coordinators (MCD officials) and Zone Operations Leads (Khelo Tech officials), functioning jointly at the Zonal level across all 12 MCD Zones; and (iv) Club Managers and External Club Supervisors at the Club level.

## 2.2 Authority and Approval Hierarchy

| Level | Authority | Scope of Decision-Making |
| --- | --- | --- |
| 1 | MCD Commissioner / Director (Education) | Policy issuance, notice authorization, final escalation authority |
| 2 | League Director | Final Club approval/rejection, fee waivers, dispute adjudication, appeals |
| 3 | Zone Coordinator (MCD) | Zone-level document verification, school authenticity, cluster validity |
| 4 | Zone Operations Lead (Khelo Tech) | Cluster facilitation, supervisor assignment, day-to-day operations |
| 5 | Club Manager | Club-level registration, roster submission, document upload |
| 6 | External Club Supervisor | Independent oversight, attendance and conduct verification, grievance escalation |

## 2.3 Delegation Matrix

The Commissioner delegates day-to-day registration administration to the League Director. The League Director delegates Zone-level verification to Zone Coordinators and operational execution to Zone Operations Leads. No individual functionary may approve a Club application in which they, a relative, or their employing institution holds a direct interest; such cases must be escalated to the next higher authority.

## 2.4 Escalation Matrix

| Issue Raised At | First Escalation | Second Escalation | Final Authority |
| --- | --- | --- | --- |
| Club Manager | Zone Operations Lead | Zone Coordinator | League Director |
| Zone Coordinator | League Director | MCD Director (Education) | MCD Commissioner |
| External Club Supervisor | Zone Operations Lead | Zone Coordinator | League Director |
| Inter-Zone / Policy Dispute | League Director | MCD Director (Education) | MCD Commissioner |

## 2.5 Roles and Responsibilities

| Activity | Club Manager | Zone Coordinator | League Director | ECS |
| --- | --- | --- | --- | --- |
| Document Upload | R | I | I | I |
| Zone Verification | C | R/A | I | I |
| Final Approval | I | C | R/A | I |
| Age Verification (spot) | C | I | I | R |
| Fee Confirmation | R | C | A | I |
| Appeals Adjudication | I | C | R/A | I |

3. Eligibility Criteria

## 3.1 Eligible Institutions

•     Delhi Government (DoE) zones.

•     Recognized private zones in Delhi-NCR.

•     Sports academies with a valid registration/affiliation certificate.

•     Registered NGOs engaged in grassroots sports development.

•     Community clubs with a documented playing history and identifiable home ground.

•     Corporate-sponsored clubs, subject to Section 3.3 disclosure requirements.

## 3.2 Cluster Clubs

Two or more eligible zones may jointly form a Cluster Club where individual student strength is insufficient to field all four teams (U-9 Boys, U-9 Girls, U-11 Boys, U-11 Girls) independently, per the Club Formation Decision Matrix in Section 4.

## 3.3 Eligibility Restrictions, Disqualifications and Conflict of Interest

•     A school may be affiliated with only one Club per sport in a given season; dual affiliation renders both applications void.

•     A Club found to have submitted fraudulent age, identity, or school-affiliation documents shall be disqualified for the season and referred to the Risk Management process (Section 17).

•     No coach, parent, teacher, or principal associated with a Club may simultaneously serve as its External Club Supervisor (see Section 8.4).

•     No current MCD employee may be appointed as External Club Supervisor of any Club, to avoid perceived favoritism toward MCD Clubs.

•     A Club under active suspension from a prior season may not re-register until the suspension period lapses and any outstanding fines are cleared.

# 4. Club Formation Policy

## 4.1 Guiding Principle

Every Club must field four teams per sport — U-9 Boys, U-9 Girls, U-11 Boys, and U-11 Girls — with a minimum of 8 players per team (32 players minimum per Club per sport) for the inaugural season, and an ideal strength of 12–15 players per team (48–60 players per Club per sport) thereafter.

## 4.2 Club Formation Decision Matrix

| School Strength (approx.) | Recommended Club Type | Required Action |
| --- | --- | --- |
| 1,000+ students | Single-school Club | Register independently on GMS |
| 500–1,000 students | Single-school (possible) or 2-school cluster | Attempt independent registration; request cluster if player strength is insufficient |
| 250–500 students | 2-school cluster | Must identify one partner school (Khelo Tech facilitates) |
| 100–250 students | 3-school cluster | Must identify two to three partner zones (Khelo Tech facilitates) |
| Below 100 students | Not eligible as lead; must join an existing Club | Cannot form own Club independently |

## 4.3 Single-School Clubs

A single school with sufficient player strength may form and field its own Club under the naming convention '[School Name] Club' (e.g., 'DPS RK Puram Club'), registering independently through the GMS portal.

## 4.4 Multi-School Cluster Clubs

Where 2–3 zones pool players to jointly field a complete Club, the Cluster must be formalized through a signed Cluster Agreement (Section 12; template at Section 19), naming a single Club Manager on a rotating annual basis, and registering as one Club entity on GMS.

## 4.5 Special Category Clubs

•     Boys-only or girls-only zones must partner with a nearby school of the complementary gender profile to field a complete four-team roster (Special Cluster).

•     zones with only a primary section (lacking U-11 strength) must partner with another school to complete their age-category coverage (Partial Cluster).

## 4.6 Naming Conventions

| Club Type | Naming Convention | Example |
| --- | --- | --- |
| Single-school Club | [School Name] Club | Springdales Club |
| Joint cluster (2 zones) | [Initials A]-[Initials B] Club or chosen name | RK-PS Club / North Delhi United |
| Micro cluster (3+ zones) | [Zone Name] [Chosen Name] Club | Civil Lines Champions Club |

NOTE: Club names require Zone Coordinator approval to prevent duplication, offensive naming, or unauthorized brand association.

## 4.7 Distance, Pooling, and Gender Inclusion

•     Cluster partner zones are identified within a 3 km radius by the Zone Operations Lead to keep practice logistics viable.

•     Player pooling across cluster zones must maintain proportional representation from each participating school, subject to merit-based team selection by the External Club Supervisor's oversight.

•     Every Club must field both Boys' and Girls' teams in both age categories; a Club unable to meet gender-inclusion requirements independently must form a cluster to do so.

## 4.8 Club Dissolution, Mergers, Renaming, Ownership and Succession

•     Dissolution: A Club may be dissolved by mutual written consent of all constituent zones, submitted to the Zone Coordinator; players are released to re-register with another eligible Club within the current registration window.

•     Mergers: Two Clubs may merge only before the Player Registration deadline, subject to League Director approval and a revised Cluster Agreement.

•     Renaming: Any change of Club name after initial approval requires a fresh Zone Coordinator naming clearance.

•     Ownership: A Club's registration is held in trust for its constituent school(s); no individual may claim personal ownership of Club branding, GMS credentials, or player data.

•     Succession: On rotation of the Club Manager (annual, per the Cluster Agreement), GMS access and all Club records transfer formally to the incoming Manager with Zone Coordinator countersignature.

# 5. Registration Process — End-to-End Workflow

## 5.1 Workflow Overview

The registration process flows sequentially: Government Notice (MCD/DoE) → Expression of Interest → Registration Portal (GMS) access → Club Creation → Document Upload → Verification → Fee Payment → Approval → Player Registration → Activation → Fixture Eligibility. Each stage below specifies its purpose, inputs, outputs, responsible party, timeline, system status, approval authority, required documents, and decision criteria.

## 5.2 Stage-wise Specification

| Stage | Responsible | Timeline | System Status |
| --- | --- | --- | --- |
| 1. Government Notice issued | MCD Commissioner / DoE | Week 0 | N/A |
| 2. Expression of Interest submitted | School Principal | Week 1–2 | Intent Received |
| 3. GMS Portal registration (OTP login) | School Principal | Week 1–2 | Account Created |
| 4. Club type selection (single/cluster) | School Principal | Week 2 | Club Type Selected |
| 5. Cluster facilitation (if required) | Zone Operations Lead | Week 2–3 | Cluster Formation in Progress |
| 6. Club profile creation | Club Manager | Week 2–3 | Profile Created |
| 7. Document upload | Club Manager | Week 3 | Documents Uploaded |
| 8. Fee payment (non-MCD Clubs) | Club Manager | Week 3 | Payment Received |
| 9. Zone Coordinator verification | Zone Coordinator | Week 3–4 | Under Review → Approved |
| 10. League Director final approval | League Director | Week 4 | Approved |
| 11. Player registration | Club Manager | Week 4–5 | Player Registration Open |
| 12. Team formation (4 teams) | Club Manager | Week 5 | Teams Formed |
| 13. Activation / Ready for League | System (GMS) | Week 5 | Ready for League |

Decision criteria at each verification checkpoint are governed by the Verification Process (Section 9) and the Document Verification Matrix (Section 7.1). A Club may not progress to the next stage until the system status of the current stage reads 'Approved' or its equivalent positive outcome.

6. Registration Portal (GMS) Workflow

## 6.1 Portal Access and Authentication

•     Portal Login: School Principal or nominated Club Manager logs in using a registered mobile number/email.

•     OTP Verification: A one-time password is issued to the registered mobile number for two-factor authentication at login and at key transaction points (fee payment, final submission).

•     School Registration: First-time users complete a school profile (UDISE code or equivalent, address, principal details) before Club creation is enabled.

## 6.2 Core Portal Modules

| Module | Function |
| --- | --- |
| Club Creation | Captures Club type, constituent school(s), naming, and category selection |
| Document Upload | Secure upload of all mandatory documents (Section 7) with format validation |
| Dashboard | Real-time status of registration stage, pending actions, and deadlines |
| Notifications | In-portal alerts for status changes and pending requirements |
| Application Tracking | Unique application ID with full stage-wise timestamp history |
| Digital Signatures | e-signature capture for authorization forms and declarations |
| Payment Gateway | Integrated UPI / Net Banking / Card / NEFT-RTGS payment processing |
| Approval Tracking | Visible chain of custody showing which authority approved which stage |
| Email & SMS Automation | Automated status-change communication to Club Manager and ECS |
| Role-Based Access Control | Differentiated permissions for Club Manager, ZC, ZOL, ECS, League Director |
| Audit Logs | Immutable timestamped log of every action taken on a Club record |

## 6.3 Status Change and Communication Protocol

Every status transition in GMS (see Section 13 for the full lifecycle) automatically triggers an SMS and email notification to the Club Manager and, where applicable, to the assigned External Club Supervisor and Zone Coordinator. All actions are recorded in the audit log with user ID, timestamp, and IP address for accountability.

# 7. Required Documents

## 7.1 Document Verification Matrix

| Document | Submitted By | Verified By | Mandatory |
| --- | --- | --- | --- |
| School recognition certificate | School Principal | Zone Coordinator | Yes |
| Principal authorization letter | School Principal | Zone Coordinator | Yes |
| Club Manager nomination form | School / Cluster zones | Zone Coordinator | Yes |
| Coaching staff details & credentials | Club Manager | Zone Coordinator | Yes |
| Ground ownership / access proof | Club Manager | Zone Coordinator | Yes |
| Player medical declaration | Parent/Guardian, per player | System + ECS | Yes |
| Code of Conduct undertaking | Club Manager, coaches, ECS | Zone Coordinator | Yes |
| Player identity/age proof (birth certificate, Aadhaar, or school leaving certificate) | Parent/Guardian, per player | System + Zone Coordinator | Yes |
| Cluster Agreement (clusters only) | Constituent zones | Zone Coordinator | Conditional |
| Bank details for fee refunds/settlements | Club Manager | League Finance Team | Yes |
| GST registration (where applicable) | Corporate/registered clubs | League Finance Team | Conditional |
| Digital declaration of no conflict of interest | External Club Supervisor | Zone Operations Lead | Yes |

NOTE: All documents must be uploaded in the format and size specified on the GMS portal. Illegible, incomplete, or tampered documents will be marked 'Action Required' under the Verification Process (Section 9).

# 8. Registration Fee Policy

## 8.1 Fee Structure

| Participation Option | Football Only | Cricket Only | Both Sports |
| --- | --- | --- | --- |
| Standard Registration (Non-MCD Club) | ₹25,000 | ₹25,000 | ₹50,000 |
| MCD Club | Nil (CSR-subsidized) | Nil (CSR-subsidized) | Nil (CSR-subsidized) |

## 8.2 Government and CSR Subsidies

The 12 pre-formed MCD Clubs participate at zero registration fee, funded through CSR subsidization. Non-MCD Clubs from economically disadvantaged Government zones may apply for a partial fee waiver through the League Director, subject to available CSR allocation for the season.

## 8.3 Refund, Late Fee, Cancellation and Transfer

•     Refund Policy: Full refund if a Club's application is rejected at Zone Coordinator or League Director verification through no fault of the applicant; no refund once a Club reaches 'Approved' status and player registration has commenced.

•     Late Fee: Applications submitted after the notified deadline attract a late fee as specified in the annual registration calendar (Section 14), subject to League Director discretion.

•     Cancellation Fee: A Club voluntarily withdrawing after payment but before approval forfeits 25% of the registration fee as a processing charge.

•     Transfer Fee: Fees paid are non-transferable between Clubs except in the case of an approved Club merger (Section 4.8).

## 8.4 Payment, Invoicing and Financial Approvals

•     Payment Modes: UPI, Net Banking, Credit/Debit Card, NEFT/RTGS, or Demand Draft (for institutions without digital payment access).

•     Invoice Generation: GMS auto-generates a GST-compliant invoice on successful payment.

•     GST Applicability: Applicable as per prevailing government norms for the registering entity type; corporate-sponsored Clubs must furnish GST details where applicable.

•     Receipt Generation: A digital receipt is issued instantly and stored in the Club's GMS document repository.

•     Financial Approvals: All fee waivers and refunds require League Director sign-off and are logged for audit (Section 16).

# 9. Verification Process

## 9.1 Multi-Layer Verification

| Layer | Verifier | What Is Verified | Timeline | Possible Outcomes |
| --- | --- | --- | --- | --- |
| 1 — System | GMS (automated) | Document format, mandatory fields, age-format validity, duplicate entries | Instant | Pass / Fail with error list |
| 2 — Zone | Zone Coordinator (MCD) | School authenticity, zone alignment, cluster validity, document genuineness | 48 hours | Approved / Action Required / Rejected |
| 3 — Central | League Director | Fee confirmation (non-MCD), special cases, dispute resolution | 24 hours | Final approval |
| 4 — Spot / Field | External Club Supervisor | On-match-day age verification, school affiliation | Throughout season | Pass / Refer for review |

## 9.2 Age Verification Protocol (U-9 & U-11)

| Step | Action | Responsible | Document Accepted |
| --- | --- | --- | --- |
| 1 | Upload age proof during player registration | Club Manager | Birth certificate / Aadhaar / School leaving certificate |
| 2 | Automated date-of-birth validation against category cut-off | System (GMS) | N/A |
| 3 | Review of system-flagged players | Zone Coordinator | Original document on request |
| 4 | Random spot check at matches (10% of players) | External Club Supervisor | Original document required |
| 5 | Disputed case escalation | League Director | Medical/age certificate from authorized hospital |

## 9.3 Verification Outcomes and Timelines

| Status | Meaning | Next Action | Timeline |
| --- | --- | --- | --- |
| Approved | Club meets all criteria | Proceed to player registration | Immediate |
| Action Required | Missing documents or errors | Resubmit corrected documents | Within 5 calendar days |
| Rejected | Does not meet eligibility criteria | Appeal to League Director | Within 7 calendar days |

# 10. Club Approval Process

## 10.1 Approval Workflow

On successful clearance of all four verification layers, the League Director issues final Club approval within GMS, activating the Player Registration module. Approval may be granted in one of three forms:

•     Conditional Approval — granted where minor, non-blocking deficiencies remain (e.g., pending bank details), with a defined cure period.

•     Provisional Approval — granted ahead of full document verification to allow player registration to begin within tight seasonal timelines, subject to retrospective confirmation within 10 days.

•     Final Approval — granted once all layers of verification are complete and no deficiencies remain.

## 10.2 Rejection and Appeal

A rejected Club may file a written appeal to the League Director within 7 calendar days of rejection, accompanied by corrected or additional documentation. The League Director shall issue a decision within 10 calendar days of receipt of the appeal. The League Director's decision on appeal is final at the operational level, subject to further escalation per Section 2.4.

## 10.3 Approval Validity, Renewal, Suspension and Termination

•     Validity: Club approval is valid for the League season for which it is granted and does not automatically carry forward.

•     Renewal: Clubs must re-register each season; returning Clubs follow an expedited verification track where prior-season records show no compliance issues.

•     Suspension: A Club may be suspended mid-season for non-compliance per the consequence framework in Section 10.4 and Section 20.2, pending investigation.

•     Termination: A Club's registration may be terminated for serious or repeated violations (fraud, safeguarding breaches), with all matches forfeited and re-registration barred for a period determined by the League Director.

# 11. Club Manager SOP

## 11.1 Appointment and Eligibility

Each Club must nominate one Club Manager at the time of Club creation. For single-school Clubs, the Manager is nominated by the Principal. For Cluster Clubs, the Manager is nominated from one of the constituent zones on a rotating annual basis, as agreed in the Cluster Agreement (Section 12.5).

## 11.2 Authority and Responsibilities

•     Creating and maintaining the Club's GMS profile and document repository.

•     Uploading all mandatory registration and player documents within prescribed timelines.

•     Coordinating fee payment and maintaining financial records for the Club.

•     Nominating coaching staff and submitting their credentials for verification.

•     Submitting and updating the player roster, ensuring gender and age-category balance.

•     Acting as the primary point of contact for the Zone Coordinator and Zone Operations Lead.

•     Cooperating with the External Club Supervisor and providing requested records without obstruction.

## 11.3 Reporting, Replacement and Removal

•     The Club Manager reports operationally to the Zone Operations Lead and administratively to the Zone Coordinator.

•     Replacement: A Club may replace its Manager at any time by submitting a fresh nomination form countersigned by the Principal(s); GMS access transfers upon Zone Coordinator confirmation.

•     Removal: The League Director may direct removal of a Club Manager found in breach of the Code of Conduct, with an interim Manager appointed within 5 working days to avoid disruption to the Club's registration status.

## 11.4 Performance Evaluation and Compliance Obligations

Club Managers are evaluated each season on document-submission timeliness, roster accuracy, and Code of Conduct adherence. Managers must complete a mandatory declaration confirming no conflict of interest with the appointed External Club Supervisor and must facilitate all verification and audit activity under Sections 9 and 16.

# 12. Cluster Club SOP

## 12.1 Cluster Eligibility

Clusters are formed where individual school strength falls below the independent-registration threshold defined in the Club Formation Decision Matrix (Section 4.2).

## 12.2 Partner School Selection and Facilitation

| Step | Action | Responsible |
| --- | --- | --- |
| 1 | School registers intent on GMS and marks 'Need cluster partner' | School Principal |
| 2 | Khelo Tech identifies nearby zones (within 3 km radius) with similar need | Zone Operations Lead |
| 3 | Introduction call/meeting arranged between zones | Relationship Manager |
| 4 | Cluster Agreement template provided and signed | zones + Khelo Tech witness |
| 5 | Club Manager nominated from one school (rotating annually) | zones, by mutual decision |
| 6 | Cluster registered as a single Club on GMS | Club Manager |

## 12.3 Agreement

Every Cluster must execute a written Cluster Agreement (template at Section 19.3) specifying player-pooling terms, Club Manager rotation, fee-sharing, practice-venue rotation, and dispute resolution — witnessed by both a Khelo Tech representative and the Zone Coordinator.

## 12.4 Revenue Sharing, Practice Scheduling and Ground Allocation

•     Registration fees are shared among constituent zones as per mutual agreement recorded in the Cluster Agreement.

•     Practice venues rotate between constituent zones on a weekly basis unless otherwise agreed.

•     Ground allocation disputes are first referred to the Zone Coordinator for mediation before escalation to the League Director.

## 12.5 Manager Selection, Rotation, Exit and Dissolution

•     Manager Selection: Determined by mutual agreement among constituent zones at Cluster formation.

•     Rotation Policy: Club Manager responsibility rotates annually among constituent zones unless all parties agree otherwise in writing.

•     Exit Policy: A constituent school may exit a Cluster between seasons by written notice to the Zone Coordinator at least 30 days before the next registration window opens; mid-season exit requires League Director approval and does not entitle the exiting school to a fee refund.

•     Dissolution: A Cluster dissolves by mutual written consent of all constituent zones or automatically if reduced below the minimum player-strength threshold, with players eligible to re-register with another Club.

# 13. Registration Status Lifecycle

## 13.1 Complete Status List and Transition Conditions

| Status | Trigger / Transition Condition |
| --- | --- |
| Draft | Club profile created but not yet submitted |
| Submitted | Club Manager submits application for review |
| Pending Documents | One or more mandatory documents missing or invalid at System check (Layer 1) |
| Payment Pending | Documents accepted; fee payment (non-MCD) awaited |
| Verification Pending | Payment received; awaiting Zone Coordinator review (Layer 2) |
| Under Review | Zone Coordinator actively reviewing the application |
| Approved | League Director confirms final approval (Layer 3) |
| Rejected | Application fails verification and is not cured within the allowed window |
| Appealed | Club Manager files appeal against a Rejected status |
| Suspended | Club found non-compliant mid-season; registration temporarily frozen |
| Expired | Application remains in Pending Documents/Payment beyond the grace period without action |
| Withdrawn | Club Manager voluntarily withdraws the application before approval |
| Cancelled | Approved Club subsequently cancelled by League Director for cause |
| Ready for League | Player registration, team formation and supervisor assignment complete; fixture-eligible |

# 14. Timelines

## 14.1 Indicative Registration Calendar

| Activity | Indicative Week / Date |
| --- | --- |
| Release of Government Notice (MCD/DoE) | Week 0 |
| Last date for Expression of Interest / registration intent | End of Week 2 |
| Cluster facilitation window | Week 2–3 |
| Document upload and fee payment deadline | End of Week 3 |
| Zone Coordinator verification window | Week 3–4 |
| League Director final approval window | Week 4 |
| Appeals window (post-rejection) | 7 calendar days from rejection notice |
| Player registration window | Week 4–5 |
| Team formation completion | End of Week 5 |
| Fixture release | Week 6 |
| League start date | Week 7 |

## 14.2 Grace Periods and Escalation Timelines

•     A grace period of 5 calendar days is granted for curing 'Action Required' verification outcomes before the application lapses to 'Expired'.

•     Zone Coordinator review must be completed within 48 hours of document submission; delays beyond 72 hours are auto-escalated to the League Director.

•     League Director final approval must be issued within 24 hours of receiving a Zone-cleared application.

•     Appeals must be adjudicated within 10 calendar days of filing.

# 15. Compliance Framework

## 15.1 Mandatory, Operational, Financial and Technical Compliance

•     Mandatory Compliance: Adherence to MCD Education Department Scheme requirements for talent scouting participation; compliance with Khelo Bharat Niti 2025 grassroots objectives; alignment with NEP 2020's inclusion of sport in education, ensuring no child is excluded on grounds of fee.

•     Operational Compliance: Timely document submission, accurate roster maintenance, and cooperation with Zone-level verification.

•     Financial Compliance: Accurate fee payment, GST documentation where applicable, and transparent handling of any Club-level funds under External Club Supervisor oversight.

•     Technical Compliance: Use of GMS for all registration transactions; no offline or bypass registration is recognized as valid.

## 15.2 Ethical Compliance and Code of Conduct

All Club Managers, coaches, and External Club Supervisors must sign the League Code of Conduct, committing to fair play, non-discrimination, and merit-based team selection free of favoritism toward any player, parent, or constituent school within a Cluster.

## 15.3 Data Privacy, Child Protection and Safeguarding

•     All player data (identity documents, medical declarations, photographs) is collected and stored on GMS under restricted, role-based access and used solely for League administration and talent-pipeline purposes.

•     Background checks are mandatory for all coaches and support staff prior to Club approval, in line with POCSO Act requirements for protection of minors.

•     External Club Supervisors are specifically tasked with ongoing child-safety compliance monitoring and reporting any concerns to the Zone Coordinator (Section 8.5).

## 15.4 Anti-Doping and Anti-Fraud Declarations

Club Managers and coaches must submit a signed anti-fraud declaration confirming the authenticity of all submitted documents, and an age-appropriate anti-doping awareness undertaking, as part of the mandatory document set (Section 7).

# 16. Audit Framework

## 16.1 Audit Types

| Audit Type | Scope | Frequency | Conducted By |
| --- | --- | --- | --- |
| Digital Audit | GMS transaction logs, access records, status-change history | Quarterly | Khelo Tech Technology Lead |
| Document Audit | Sample review of uploaded documents for authenticity | Monthly | Zone Coordinator |
| Financial Audit | Fee collection, refunds, waivers, and CSR fund utilization | Quarterly | League Finance Team |
| Random Inspection | Unannounced Club-level document and ground checks | Ongoing | Zone Operations Lead |
| Ground Inspection | Verification of practice/match venue suitability and safety | Pre-season and ongoing | Zone Coordinator |
| Player Verification | Cross-check of roster against age/identity documents | Ongoing (10% spot-check) | External Club Supervisor |
| Attendance Audit | Match-day attendance versus registered roster | Every match | External Club Supervisor |
| Technology Audit | System uptime, data security, and access-control review | Bi-annual | Khelo Tech Technology Lead |

# 17. Risk Management

## 17.1 Identified Risks and Mitigation Plans

| Risk | Mitigation |
| --- | --- |
| Duplicate Club registrations | System-level duplicate-detection at Layer 1 verification; single-affiliation rule (Section 3.3) |
| Fake or unrecognized zones | School recognition certificate mandatory; Zone Coordinator field verification |
| Age fraud | Multi-document age proof, automated cut-off validation, 10% random spot-check by ECS, medical referral for disputed cases |
| Identity / document fraud | Anti-fraud declaration, original-document verification on request, audit sampling |
| Multiple registrations by one player | GMS cross-Club duplicate-player detection |
| Conflict of interest (Manager/Supervisor) | Eligibility restrictions (Section 3.3, 8.4) and mandatory declarations |
| Fee disputes | Transparent fee structure, GST-compliant invoicing, League Director as final arbiter |
| Cluster disputes | Written Cluster Agreement with defined dispute-resolution clause routed to Zone Coordinator |
| Cybersecurity / data breach | Role-based access control, encrypted storage, periodic technology audits |
| System failure / downtime | Documented business-continuity fallback (manual interim submission with retrospective GMS entry) |

# 18. Dispute Resolution

## 18.1 Categories of Disputes

•     Registration disputes (eligibility, document rejection).

•     Fee disputes (refunds, waivers, cancellation charges).

•     Cluster disputes (partner-school disagreements, Manager rotation conflicts).

•     Player eligibility disputes (age, affiliation, duplicate registration).

## 18.2 Appeals Committee, Jurisdiction and Timelines

An Appeals Committee, chaired by the League Director and comprising a nominated MCD representative and a Khelo Tech Operations representative, has jurisdiction over all disputes not resolved at Zone Coordinator level. Disputes must be filed within 7 calendar days of the triggering decision and are adjudicated within 10 calendar days of filing. The Appeals Committee's decision is final at the operational level, subject to escalation per the Governance Framework (Section 2.4).

# 19. Forms & Templates

## 19.1 Expression of Interest (Sample Fields)

•     School Name & UDISE Code

•     Principal Name & Contact

•     Sport(s) of Interest

•     Approximate Student Strength

•     Club Type Preference (Single-school / Cluster / Undecided)

## 19.2 Club Registration Form (Sample Fields)

•     Club Name

•     Club Type

•     Constituent School(s)

•     Club Manager Name & Contact

•     Coaching Staff Details

•     Ground/Venue Details

•     Sport(s) & Age Categories

## 19.3 Cluster Agreement (Simplified Template)

This Agreement is made on [Date] between: (1) [School A Name], represented by [Principal Name]; (2) [School B Name], represented by [Principal Name]; (3) [School C Name], represented by [Principal Name] (if applicable). The parties hereby agree to form a joint Club named '[Cluster Name] Club', on the following terms: players will be drawn from all participating zones; the Club Manager will be nominated from [School Name] for this season on an annually rotating basis; the registration fee will be shared as per mutual agreement; the practice venue will rotate weekly between zones; any dispute between zones will be resolved by the Zone Coordinator; and each school will provide at least one coach or support staff. Signed by all participating zones and witnessed by a Khelo Tech representative and the Zone Coordinator.

## 19.4 Principal Authorization (Sample Fields)

•     School Name & Letterhead

•     Authorization of named Club Manager

•     Confirmation of School's participation consent

•     Principal's Signature & School Seal

## 19.5 Manager Nomination (Sample Fields)

•     Nominee Name, Contact & ID Proof

•     Nominating School(s)

•     Declaration of No Conflict of Interest

•     Acceptance Signature

## 19.6 Declaration (Sample Fields)

•     Anti-fraud declaration re: authenticity of submitted documents

•     Code of Conduct acceptance

•     Anti-doping awareness undertaking

•     Child-safety compliance acknowledgment

## 19.7 Verification / Approval / Rejection / Appeal (Sample Fields)

•     Verification Form: Checklist reference, verifying officer, outcome, remarks.

•     Approval Letter: Club ID, approval date, approving authority, validity period.

•     Rejection Letter: Club ID, grounds for rejection, cure period (if any), appeal instructions.

•     Appeal Form: Club ID, grounds for appeal, supporting documents, requested remedy.

# 20. Annexures

## Annexure A — Registration Checklist

•     Expression of Interest submitted

•     Club type selected

•     Club profile created on GMS

•     All mandatory documents uploaded (Section 7.1)

•     Registration fee paid (non-MCD)

•     Zone Coordinator verification passed

•     League Director approval received

•     External Club Supervisor assigned

•     Player roster (minimum 8 per team) submitted

•     Age proofs verified for all players

## Annexure B — Document Checklist

Refer to the Document Verification Matrix at Section 7.1 for the complete mandatory and conditional document list by submitter and verifier.

## Annexure C — Verification Checklist

Refer to the Multi-Layer Verification table at Section 9.1 and the Age Verification Protocol at Section 9.2.

## Annexure D — Portal Workflow (Described)

Login (OTP) → School Registration → Club Creation → Document Upload → Fee Payment → Dashboard Status Tracking → Zone Verification → Central Approval → Player Registration → Team Formation → Ready for League. Each arrow represents an automated GMS status transition with corresponding SMS/email notification.

## Annexure E — Approval Flowchart (Described)

Submitted → System Check (Layer 1: Pass/Fail) → Zone Coordinator Review (Layer 2: Approved / Action Required / Rejected) → League Director Final Approval (Layer 3) → Ongoing Field Verification (Layer 4, throughout season). A 'Rejected' outcome routes to the Appeals Committee (Section 18); an 'Action Required' outcome routes back to the Club Manager for resubmission within 5 days.

## Annexure F — Club Lifecycle Diagram (Described)

Draft → Submitted → Verification Pending → Under Review → Approved → Player Registration Open → Teams Formed → Ready for League → (Season End) → Renewal or Expiry. Parallel branch states: Suspended, Rejected/Appealed, Withdrawn, Cancelled — each re-entering the main flow only on successful cure or appeal.

## Annexure G — Responsibility Matrix (RACI)

Refer to Section 2.5 for the consolidated RACI table covering document upload, zone verification, final approval, age verification, fee confirmation, and appeals adjudication.

## Annexure H — Escalation Matrix

Refer to Section 2.4 for the complete escalation path from Club Manager through Zone Coordinator, League Director, MCD Director (Education), to the MCD Commissioner.

## Annexure I — Timeline Chart

Refer to Section 14.1 for the indicative week-by-week registration calendar from Government Notice release through League start.

## Annexure J — Frequently Asked Questions

•     Q: Can a school join more than one Club? A: No — a school may be affiliated with only one Club per sport per season.

•     Q: What happens if a Club misses the document deadline? A: The application moves to 'Action Required' with a 5-day cure period, after which it lapses to 'Expired'.

•     Q: Who bears the cost of forming a Cluster? A: Constituent zones share the registration fee as agreed in the Cluster Agreement; Khelo Tech facilitation itself is free of charge.

•     Q: Can a coach also be the External Club Supervisor? A: No — this is an absolute conflict-of-interest restriction (Section 8.4).

•     Q: What if a player's age document is disputed? A: The case is escalated to the League Director, who may require a medical/age certificate from an authorized hospital (Section 9.2).

## Annexure K — Glossary

Refer to Section 1.6 (Definitions) and Section 1.7 (Abbreviations) for the complete glossary of terms used throughout this SOP.